## Sheet1
| Module | Sub-module | Start Date | Complete Date | ETA (in days)
1 | Prospective Supplier Self-Registration form (accessible from Fibrex website) |  | 2016-06-28
| Fibrex Supplier Portal (Supplier view) | Login | 2016-06-28 | 2016-06-28 | Complete
2 |  | Home Page | 2016-06-28
3 |  | Company Profile
4 |  | Change Requests History
6 | Fibrex Supplier Portal (Buyer View) | Home page
7 |  | Supplier Search page
8 |  | Registration Search page
9 |  | Registration workflow
Audit History
10 |  | Change Requests
11 |  | Internal Supplier Registration
To-Do List
12 | Notifications
13 | IMS | Supplier Update
14 |  | Interface with Supplier Portal