## List
# | Page | Description | Reproduction Scenario | Referred Figures | Type | Priority | Tester | Developer | Status | ETA | Developer's Comments | Tester's Comments
1 | FIRMS | In the Add/Edit project master, add a checkbox labelled: Create PO against this cost center? Permission linked to this field should be the same as the permission set for creating/editing the cost center Field Name: allow_po_rls Field Type: bit |  | Figure 1 | Enhancement | Medium | HIBA HALABI | Sabir ALLI | Open
2 | FSP/PO | Every instance of project field referenced in this project should populate the list from dept_master of selected division, where allow_po_rls = 1 (Duplication of code should be avoided. The changes have to be done once for all pages) |  |  | Enhancement | High | Hiba HALABI |  | Open
3 | FSP/PO | Change PONum to varchar(8). Seed = 12018 Increment:1. Maintain old code/procedure seperatly (do not overwrite) |  |  | Enhancement | High | HIBA HALABI | Mohsan | Fix Available
4 | FSP/PO | PONum should always be reflected on PO. Discard the label draft when the status = DRAFT |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available
5 | FSP/PO | Upon selecting the vendor id, populate the address automatically (editable) set to [Address 1], (concat) [Address 2], (concat) [PC: [PostalCode]] |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Fix Available
6 | FSP/PO | Add Costs to the as shown in figure 3 to the PO header, as the last column after Dates. Shorten the field size length to fit the Cost. Add the following fields in PO table. 1- CURRENCYCODE ¦ NOT NULL VARCHAR2(8) default to AED 2- TOTALTAX ¦ NUMBER(10,2) |  | Figure 3 | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available
7 | POLINE | When selecting the Line Type, the following error gets displayed: Index was out of range. Must be non-negative and less than the size of the collection. Parameter name: index |  | Figure 4 | Bug | High | HIBA HALABI | Rizwan | Open
8 | POLINE | When clicking on Add New Line, the [No Record] label remains visible. See figure 5. Update the behavior so that if the grid has no lines, the entire grid should be hidden. |  | Figure 5 | Bug | Medium | HIBA HALABI | Rizwan | Open
9 | Seach PO | Enter the Total Cost as last column of the search results. |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Fix Available
10 | POLINE | Add the fields captured on sheet 3 in POLINE db table. |  | Sheet 3 | Enhancement | High | HIBA HALABI | Mohsan | Fix Available
11 | POLINE | Add the following fields to the POLINE panel, |  |  | Enhancement | High | HIBA HALABI | Rizwan | Postponed
12 | database | Create new table TAXCODES in database with the below fields: TAXCODE NVARCHAR(5) TAXDESC NVARCHAR(250) TAXRATE number(3)/// maximum 100.00 EFFDATE DATE |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available
13 | POLINE | When editing values within POLINE, it should (in parallel) edit the field in the expanded panel. Note: check behavior in maximo for reference. |  |  | Enhancement | Medium | HIBA HALABI | Rizwan | Open
14 | POLINE | from POLINE, when updating the description by augmenting text to the END of the existing text, changes are discarded |  |  | Bug | Very High | HIBA HALABI | Rizwan | Open
15 | POLINE | Add MASKING to all numbers in the grid, with 2 decimals. E.g. 270,000.00. Update corresponding field types in the database accordingly. Rounding is required to achieve the required precision. |  |  | Bug | Very High | HIBA HALABI | Rizwan | Open
16 | POLINE | Remove the SAVE/CANCEL buttons from panel, and the equivelant buttons on the POLINE, highlighted in figure 6. Only one save button is required at the top of the page. |  | Figure 6 | Enhancement | Very High | HIBA HALABI | Rizwan | Open
17 | POLINE | Once user clicks on Add New Line, the panel should expand by default, nullified, instead of reflecting a previously expanded row. |  |  | Bug | Medium | HIBA HALABI | Rizwan | Open
18 | POLINE | Auto-update of poline fields when updating LINEQTY, UNITPRICE, and LINECOST. -If Quantity is updated, and Unit Cost is defined, update LINECOST. - If Quantity is updated, and Unit Cost is null or empty or zero, and LINECOST is defined-> update Unit Cost - If Unit Cost is updated, and Quantity is defined, update LINECOST. - If Unit Cost is updated, and Quantity is null or empty or zero, and LINE COST is defined -> update Quantity. - If LINECOST is updated, and Quantity is defined -> update Unit Cost. - If LINECOST is updated, and Quantity is null or empty or zero, and UNIT COST is defined -> update Quantity. It should be possible to define LINECOST while leaving unit cost and quantity null. | for reference, mimic the same behavior in maximo. |  | Enhancement | Medium | HIBA HALABI | Rizwan | Open

## Figures
Figure 1
Figure 2
Figure 3
Figure 4
Figure 5
Figure 6

## POLINE fields
PONUM NOT NULL VARCHAR2(8) | x
ITEMNUM VARCHAR2(30)
MODELNUM VARCHAR2(8)
CATALOGCODE VARCHAR2(30)
ORDERQTY NUMBER(15,2) | x
ORDERUNIT VARCHAR2(8) | x
UNITCOST NUMBER(10,2) | x
RECEIVEDQTY NUMBER(15,2)
RECEIVEDUNITCOST NUMBER(10,2)
RECEIVEDTOTALCOST NOT NULL NUMBER(10,2)
REJECTEDQTY NOT NULL NUMBER(15,2)
VENDELIVERYDATE DATE
ENTERDATE NOT NULL DATE | x
ENTERBY NOT NULL VARCHAR2(30) | x
DESCRIPTION VARCHAR2(100) | x | change from ITEMDESCRIPTION to DESCRIPTION
REQUESTEDBY VARCHAR2(30)
REQDELIVERYDATE DATE
POLINENUM NOT NULL NUMBER | x
LINECOST NOT NULL NUMBER(10,2) | x
BRAND VARCHAR2(20)
CATEGORY VARCHAR2(16)
REMARK VARCHAR2(100)
POLINEID NOT NULL NUMBER
LINETYPE NOT NULL VARCHAR2(15) | x
ROWSTAMP NOT NULL VARCHAR2(40) | x
TAXCODE VARCHAR2(5)
TAXTOTAL NUMBER(10,2)
TAXED NOT NULL BIT
COSTCODE | x

## Sheet1
Currency | AED | UAE Dirham
Currency | AFN | Afghani
Currency | ALL | Lek
Currency | AMD | Armenian Dram
Currency | ANG | Netherlands Antillean Guilder
Currency | AOA | Kwanza
Currency | ARS | Argentine Peso
Currency | AUD | Australian Dollar
Currency | AWG | Aruban Florin
Currency | AZN | Azerbaijanian Manat
Currency | BAM | Convertible Mark
Currency | BBD | Barbados Dollar
Currency | BDT | Taka
Currency | BGN | Bulgarian Lev
Currency | BHD | Bahraini Dinar
Currency | BIF | Burundi Franc
Currency | BMD | Bermudian Dollar
Currency | BND | Brunei Dollar
Currency | BOB | Boliviano
Currency | BOV | Mvdol
Currency | BRL | Brazilian Real
Currency | BSD | Bahamian Dollar
Currency | BTN | Ngultrum
Currency | BWP | Pula
Currency | BYR | Belarussian Ruble
Currency | BZD | Belize Dollar
Currency | CAD | Canadian Dollar
Currency | CDF | Congolese Franc
Currency | CHE | WIR Euro
Currency | CHF | Swiss Franc
Currency | CHF | Swiss Franc
Currency | CHW | WIR Franc
Currency | CLF | Unidad de Fomento
Currency | CLP | Chilean Peso
Currency | CNY | Yuan Renminbi
Currency | COP | Colombian Peso
Currency | COU | Unidad de Valor Real
Currency | CRC | Costa Rican Colon
Currency | CUC | Peso Convertible
Currency | CUP | Cuban Peso
Currency | CVE | Cabo Verde Escudo
Currency | CZK | Czech Koruna
Currency | DJF | Djibouti Franc
Currency | DKK | Danish Krone
Currency | DOP | Dominican Peso
Currency | DZD | Algerian Dinar
Currency | EGP | Egyptian Pound
Currency | ERN | Nakfa
Currency | ETB | Ethiopian Birr
Currency | EUR | Euro
Currency | FJD | Fiji Dollar
Currency | FKP | Falkland Islands Pound
Currency | GBP | Pound Sterling
Currency | GEL | Lari
Currency | GHS | Ghana Cedi
Currency | GIP | Gibraltar Pound
Currency | GMD | Dalasi
Currency | GNF | Guinea Franc
Currency | GTQ | Quetzal
Currency | GYD | Guyana Dollar
Currency | HKD | Hong Kong Dollar
Currency | HNL | Lempira
Currency | HRK | Kuna
Currency | HTG | Gourde
Currency | HUF | Forint
Currency | IDR | Rupiah
Currency | ILS | New Israeli Sheqel
Currency | INR | Indian Rupee
Currency | IQD | Iraqi Dinar
Currency | IRR | Iranian Rial
Currency | ISK | Iceland Krona
Currency | JMD | Jamaican Dollar
Currency | JOD | Jordanian Dinar
Currency | JPY | Yen
Currency | KES | Kenyan Shilling
Currency | KGS | Som
Currency | KHR | Riel
Currency | KMF | Comoro Franc
Currency | KPW | North Korean Won
Currency | KRW | Won
Currency | KWD | Kuwaiti Dinar
Currency | KYD | Cayman Islands Dollar
Currency | KZT | Tenge
Currency | LAK | Kip
Currency | LBP | Lebanese Pound
Currency | LKR | Sri Lanka Rupee
Currency | LRD | Liberian Dollar
Currency | LSL | Loti
Currency | LYD | Libyan Dinar
Currency | MAD | Moroccan Dirham
Currency | MAD | Moroccan Dirham
Currency | MDL | Moldovan Leu
Currency | MGA | Malagasy Ariary
Currency | MKD | Denar
Currency | MMK | Kyat
Currency | MNT | Tugrik
Currency | MOP | Pataca
Currency | MRO | Ouguiya
Currency | MUR | Mauritius Rupee
Currency | MVR | Rufiyaa
Currency | MWK | Kwacha
Currency | MXN | Mexican Peso
Currency | MXV | Mexican Unidad de Inversion (UDI)
Currency | MYR | Malaysian Ringgit
Currency | MZN | Mozambique Metical
Currency | NAD | Namibia Dollar
Currency | NGN | Naira
Currency | NIO | Cordoba Oro
Currency | NOK | Norwegian Krone
Currency | NPR | Nepalese Rupee
Currency | NZD | New Zealand Dollar
Currency | OMR | Rial Omani
Currency | PAB | Balboa
Currency | PEN | Nuevo Sol
Currency | PGK | Kina
Currency | PHP | Philippine Peso
Currency | PKR | Pakistan Rupee
Currency | PLN | Zloty
Currency | PYG | Guarani
Currency | QAR | Qatari Rial
Currency | RON | Romanian Leu
Currency | RSD | Serbian Dinar
Currency | RUB | Russian Ruble
Currency | RWF | Rwanda Franc
Currency | SAR | Saudi Riyal
Currency | SBD | Solomon Islands Dollar
Currency | SCR | Seychelles Rupee
Currency | SDG | Sudanese Pound
Currency | SEK | Swedish Krona
Currency | SGD | Singapore Dollar
Currency | SHP | Saint Helena Pound
Currency | SLL | Leone
Currency | SOS | Somali Shilling
Currency | SRD | Surinam Dollar
Currency | SSP | South Sudanese Pound
Currency | STD | Dobra
Currency | SVC | El Salvador Colon
Currency | SYP | Syrian Pound
Currency | SZL | Lilangeni
Currency | THB | Baht
Currency | TJS | Somoni
Currency | TMT | Turkmenistan New Manat
Currency | TND | Tunisian Dinar
Currency | TOP | Pa’anga
Currency | TRY | Turkish Lira
Currency | TTD | Trinidad and Tobago Dollar
Currency | TWD | New Taiwan Dollar
Currency | TZS | Tanzanian Shilling
Currency | UAH | Hryvnia
Currency | UGX | Uganda Shilling
Currency | USD | US Dollar
Currency | UYI | Uruguay Peso en Unidades Indexadas
Currency | UYU | Peso Uruguayo
Currency | UZS | Uzbekistan Sum
Currency | VEF | Bolivar
Currency | VND | Dong
Currency | VUV | Vatu
Currency | WST | Tala
Currency | XAF | CFA Franc BEAC
Currency | XCD | East Caribbean Dollar
Currency | XOF | CFA Franc BCEAO
Currency | XPF | CFP Franc
Currency | XSU | Sucre
Currency | XUA | ADB Unit of Account
Currency | YER | Yemeni Rial
Currency | ZAR | Rand
Currency | ZMW | Zambian Kwacha
Currency | ZWL | Zimbabwe Dollar

## Sheet2 (hidden)
Type | Priority | Status
Bug | Low | Open
Regression | Medium | Fix Available
Enhancement | High | Failed
New Development | Very High | Passed
Missing Function |  | Cannot Reproduce
Cancelled
Postponed