## List
# | Page | Description | Reproduction Scenario | Referred Figures | Type | Priority | Tester | Developer | Status | ETA | Developer's Comments | Tester's Comments
1 | FIRMS/COST CENTER | In the Add/Edit project master, add a checkbox labelled: Create PO against this cost center? Permission linked to this field should be the same as the permission set for creating/editing the cost center Field Name: allow_po_rls Field Type: bit |  | Figure 1 | Enhancement | Medium | HIBA HALABI | Sabir ALLI | Passed
2 | FSP/PO | Every instance of project field referenced in this project should populate the list from dept_master of selected division, where allow_po_rls = 1 (Duplication of code should be avoided. The changes have to be done once for all pages) For lists of project, add condition to populate active projects only, where depm_project_status = '0'. (inactive projects have code '0') |  |  | Enhancement | High | Hiba HALABI | Mohsan | Fix Available |  |  | Apply same validation on PO save as well.
3 | FSP/PO | Change PONum to varchar(8). Seed = 12018 Increment:1. Maintain old code/procedure seperatly (do not overwrite) |  |  | Enhancement | High | HIBA HALABI | Mohsan | Passed
4 | FSP/PO | PONum should always be reflected on PO. Discard the label draft when the status = DRAFT |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Passed
5 | FSP/PO | Upon selecting the vendor id, populate the address automatically (editable) set to [Address 1], (concat) [Address 2], (concat) [PC: [PostalCode]] |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Passed
6 | FSP/PO | Add Costs to the PO header page as shown in figure 3, as the last column after Dates. Shorten the field size length to fit the Cost. Add the following fields in PO table. 1- CURRENCYCODE ¦ NOT NULL VARCHAR2(8) default to AED 2- TOTALTAX ¦ NUMBER(10,2) |  | Figure 3 | Enhancement | Medium | HIBA HALABI | Mohsan | Passed
7 | POLINE | When selecting the Line Type, the following error gets displayed: Index was out of range. Must be non-negative and less than the size of the collection. Parameter name: index |  | Figure 4 | Bug | High | HIBA HALABI | Rizwan | Passed
8 | POLINE | When clicking on Add New Line, the [No Record] label remains visible. See figure 5. Update the behavior so that if the grid has no lines, the entire grid should be hidden. |  | Figure 5 | Bug | Medium | HIBA HALABI | Rizwan | Passed
9 | Seach PO | Enter the Total Cost as last column of the search results. |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Passed
10 | POLINE | Add the fields captured on sheet 3 in POLINE db table. |  | Sheet 3 | Enhancement | High | HIBA HALABI | Mohsan | Passed |  |  | Add Cost Code as freettext. Design issues already discussed with Mohsan.
11 | POLINE | Update the POLINE ITEM panel. See figure 7. fields in grey should be disabled |  | Figure 7 | Enhancement | High | HIBA HALABI | Rizwan | Passed
12 | database | Create new table TAXCODES in database with the below fields: ID smallint; identifier PRIMARY KEY TAXCODE NVARCHAR(5) TAXDESC NVARCHAR(250) TAXRATE number(3)/// maximum 100.00 EFFDATE DATE |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available |  |  | Add ID smallint; identifier PRIMARY KEY TAXCODE NVARCHAR(5) not TAXCODEID -- make sure to correct all references
13 | POLINE | When editing values within POLINE, it should (in parallel) edit the field in the expanded panel. Note: check behavior in maximo for reference. |  |  | Enhancement | Medium | HIBA HALABI | Rizwan | Passed
14 | POLINE | from POLINE, when updating the description by augmenting text to the END of the existing text, changes are discarded |  |  | Bug | Very High | HIBA HALABI | Rizwan | Passed
15 | POLINE | Add MASKING to all numbers in the grid, with 2 decimals. E.g. 270,000.00. Update corresponding field types in the database accordingly. Rounding is required to achieve the required precision. |  |  | Bug | Very High | HIBA HALABI | Rizwan | Passed
16 | POLINE | Remove the SAVE/CANCEL buttons from panel, and the equivelant buttons on the POLINE, highlighted in figure 6. Only one save button is required at the top of the page. |  | Figure 6 | Enhancement | Very High | HIBA HALABI | Rizwan | Passed |  | Error upon clicking on Update.
17 | POLINE | Once user clicks on Add New Line, the panel should expand by default, nullified, instead of reflecting a previously expanded row. |  |  | Bug | Medium | HIBA HALABI | Rizwan | Passed
18 | POLINE | Auto-update of poline fields when updating LINEQTY, UNITPRICE, and LINECOST. -If Quantity is updated, and Unit Cost is defined, update LINECOST. - If Quantity is updated, and Unit Cost is null or empty or zero, and LINECOST is defined-> update Unit Cost - If Unit Cost is updated, and Quantity is defined, update LINECOST. - If Unit Cost is updated, and Quantity is null or empty or zero, and LINE COST is defined -> update Quantity. - If LINECOST is updated, and Quantity is defined -> update Unit Cost. - If LINECOST is updated, and Quantity is null or empty or zero, and UNIT COST is defined -> update Quantity. It should be possible to define LINECOST while leaving unit cost and quantity null. | for reference, mimic the same behavior in maximo. |  | Enhancement | Medium | HIBA HALABI | Rizwan | Failed |  | All issues highlighted in red are still pending, that is if Quantity of Unit Cost is null. To reproduce, open any PO. Nullify the quantity from POLINE 1. Update UnitCost. Epected behavior: Quantity = Line Cost/Unit Cost. Not achieved. Similar behavior expected when Unit Cost is nullified.
19 | FIRMS/ORG MASTER | Add to security.dbo.ORG_MASTER 2 new fields: org_abbr_name VARCHAR(8) -- amend after org_name -- mark as key (no duplicates allowed) org_is_po_active bit -- amend at the end |  |  | Enhancement | High | HIBA HALABI | Sabir ALLI | Passed
20 | PO | For all references of Organization in the system, select org_code, org_abbr_name, org_name from security.dbo.ORG_MASTER where org_is_po_active = 1 |  |  | Enhancement | High | HIBA HALABI | Mohsan | Failed |  | Failed. Apply validation rule on SAVE page as well.
21 | PO | For all reference to Organization field, if user types the corg_abbr_name/org_name, system should correctly identfify the user selection. If user enters an un-identified value, throw an error. |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Passed
22 | Currency db | Add table CURRENCY in database with the below fields ID smallint; identifier PRIMARY KEY CURRENCYCODE NOT NULL CHAR(3) CURRENCYDESC NOT NULL VARCHAR(254) |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available |  |  | Encoded in SS_ALNDOMAIN
23 | FIRMS/MRV | In MRV, the PO should be mandatory. The field should be associated with a search option, which reads from fsppo.dbo.vw_po - On post-edit, evaluate the field value. - If PO does not exist, return error: PO number does not exist. - If PO Status <> 'APRV' return error XXXXXXXXXXXXXXx |  |  | Enhancement | High | Hiba HALABI | Sabir ALLI | Open
24 | FIRMS/MRV | In MRV lines, add PO Line Num to grid as the first column (before Item num). - If PONum <> NULL, PO Line Num should be mandatory - If PO Line Num does not exist in fsppo.dbo.vw_poline for the selected PO Number, return "This purchase order line number does not exist in the purchase order." Implement on POSTEDIT/POSTUPDATE - If the POLINETYPE of the entered POLINE NUM <> 'ITEM', return error: "This purchase order line number references a service." - Auto-populate the PO LIne description in the POLINEDESC field. |  | Figure 8 | Enhancement | High | Hiba HALABI | Sabir ALLI | Open
25 | FIRMS/MRV | The MRV Supplier Account code should match that of PO. Match Supplier Number from Account code to vw_po.VENDORID. >>>>>>>>>>> HOW? |  | Figure 8 | Enhancement | High | Hiba HALABI | Sabir ALLI | Open
26 | FIRMS/MRV | In MRV lines, upon entering a PO LINE num, if the quantity is greater than the vx_poline.ORDERQTY - vx_poline.RECEIVEDQTY, return an error. |  | Figure 8 | Enhancement | Medium | Hiba HALABI | Sabir ALLI | Open
27 | PO | Create new table TAXCODES in database with the below fields: ID smallint; identifier PRIMARY KEY TAXCODE NVARCHAR(5) TAXDESC NVARCHAR(250) TAXRATE number(3)/// maximum 100.00 EFFDATE DATE |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Cancelled |  |  | Duplciate anomaly
28 | POLINE | In the POLINE remarks fields, if user enters ENTER, the PO will be saved. Correct the behavior ENTER should never save the page, unless the button is clicked. |  |  | Bug | Medium | Hiba HALABI | Rizwan | Passed
29 | POLINE | Upon saving the PO, the POLINE total cost should be re-calculated, and costs updated. This is very important to avoid scenarios like that of PO # 12021, where the total cost of line 1 is not equal to quantity x unit cost, and hence the related costs and incorrect as well. |  |  | Bug | High | Hiba HALABI | Rizwan | Passed
30 | POLINE | POLINE UNIT, LINE TYPE, DESCRIPTION is mandatory. Return error otherwise upon saving. All errors should be encoded in SS_Messages for ease of update. If PO LINE TYPE = ITEM ¦ Manpower, then the quantity field should be mandatory. |  |  | Enhancement | High | Hiba HALABI | Rizwan | Failed |  |  | UOM should be mandatory.
31 | POLINE | When double-clicking on a POLINE in order to update its values, the actual PO LINE TYPE value is not selected. Instead, the 'ITEM' value is selected. | To reproduce, go to PO #12021, POLINE 2, and double click. Instead of displaying MANPWR as LINE TYPE, the value ITEM is displayed. |  | Bug | Medium | Hiba HALABI | Rizwan | Passed
32 | POLINE | Add column named [Tax] after the line cost. The default TAXCODE should be set to VAT, which is rated at 5%. Thus, the default tax cost should be a 5% of the line cost. If Tax Exempt checkbox is selected, the TAXCODE field becomes disabled, and tax cost is nullified. |  |  | Enhancement | Medium | Hiba HALABI | Rizwan | Failed |  |  | Tax column not added. Remoe Cost Code column from grid. Add Tax after Line Cost
33 | POLINE | When deleting a POLINE, the line gets deleted, and the PO page is returning message: PO is being saved, although in fact it is not saving. Remove the message. It should not be displayed. |  |  | Bug | Medium | Hiba HALABI | Rizwan | Passed
34 | POLINE | When deleting a POLINE, the same POLINE NUM is being used for a newly created row. Correct this behavior. The same ID cannot be used. To reproduce, delete a row line #2, and before clicking update, add a new line, the system will show POLINE num as 3 for the newly created row. But when saved in database, it will be saved with ID 2. Incorrect behavior. It should be saved as 3. that is as per the value stored for POLINE num in the temporary table and not as per the database. |  |  | Bug | Very High | Hiba HALABI | Rizwan | Passed |  |  | When user enters a POLINE NUM which is acceptable by the system, i.e. not a duplicate value, then system should use this value and not an autogenerated number. Otherwise, if the user enters an existing POLINE NUM, system should immediately on postedit/save return error Duplicate POLINE number. Encode the error in the database.
35 | View Purchase Order Status History | Error upon clicking on View Purchase Order History. |  |  | Bug | High | Hiba HALABI | Rizwan | Passed
36 | POLINE | Revise the design to that in Figure 9. Note that the POLINE header fields like PO Num, Revision, Total Cost, etc should be shortened in width, as reflected in the image. |  | Figure 9 | Enhancement | High | Hiba HALABI | Rizwan | Open |  |  | Line Tax?
37 | POLINE | General Rules: - If Tax Emept is selected, then Tax Code is nullified and disabled, and Tax amount is reset to 0.0 and disabled. If Tax Exempt chechbox is unselected, Tax & Tax Codes become enabled. - Material Receipt checkbos and Quantity Received should be disabled. - Audit fields should be disabled. Only upon saving a poline, the audit information gets populated in db, and reflected on POLINE Item. - The Classification field should populate the corresponding values from ALN_DOMAIN table under domain_name = 'POCLASSIFICATION'. Follow same pop-up design for search page with other pages in application. - For Requested By field, when clicking on the search icon, it should populate the employee code and employee name from FIRMS.fibrexho.dbo.vw_employee_table. |  |  | Enhancement | High | HIBA HALABI | Rizwan | Open |  |  | Audit information on POLINE are not reflected In red, not done. In grey, cancelled.
38 | PO | In PO page, the Buyer field should read from vw_employee_table and not Supplier Portal users. |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Passed
39 | Seach PO | Add Currency as last column to the search results. |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Passed
40 | Contracts | Remove Contract Terms. |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Passed
41 | Conracts | Add Change Status, with no workflow, capturing the below values: CANC - Cancelled CLOS - Closed EXPIRD - Expired ACT - Active DRAFT - Draft Add Action with Change Status just like Supplier page Add View Status History. For the database related tables, follow the same terminologies as that user before. |  |  | Enhancement | High | HIBA HALABI | Mohsan | Fix Available |  |  | Status not updated. Also, default status should be DRAFT not ACTIVE.
42 | Contracts | If Contract Status = Draft, the entire Contract page is editable. If Contract Status = CLOS¦ACT¦CANC¦Expired, the Contracts page fields are all disabled |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available
43 | Contracts | In the PO page, do the following changes on Contract Ref Num field: 1- If no project, Organization, and Vendor are not defined throw error: Please select the organization, project, and vendor. Contracts are populated accordingly. 2- Display contracts related to the user selection only, where contract status = ACT (a.k.a active contracts only) |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available
44 | Contracts | Contract Type should accept contract codes not description, like LOI not Letter of Intent. |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Passed
45 | Contracts | No two contracts can have the same ORIGINAL Contract number value. Throw error: A contract with the same original contract number <<contractNum>> already exists. |  |  | Bug | High | HIBA HALABI | Mohsan | Fix Available |  | The original contract number is not reflected in the error.
46 | POLINE/PO DB | Add fields REQUESTEDBYCODE, REQUESTEDBYNAME instead of REQUESTEDBY Add fields BUYERCODE, BUYERNAME instead of BUYER Add field MANUFACUTRER VARCHAR(30) and remove field BRAND. |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Passed
47 | ITEM MASTER | Create table ITEMMASTER in database with the following fields: ITEMCODE integrer not null ITEMDESC varchar(250) ORDERUNIT varchar(10) CREATEDBY CREATIONDATE |  |  | Enhancement | High | HIBA HALABI | Mohsan | Fix Available
48 | POLINE | Add ITEM in POLINE grid and expanded panel. If user clicks on the icon adjacent to ITEM field, show all items from itemmaster. If user selected a specific item, load its code, description, and UOM in the POLINE. Description becomes disabled for editing. If item code is nullified, the item description is nullified and unlocked for editing. On post update of item code, validate if the value exists; otherwise, return error Item code does not exist, and highlight the field in red. See figure 16 |  | Figure 16 | Enhancement | High | HIBA HALABI | Rizwan | Failed
49 | POLINE | Once the PO status gets approved, every poline tagged as ITEM in line type, and for which ITEMCODE is null, create a item record in the ITEMMASTER with the same ITEM DESC and UOM. Set CreatedBy to POLINE Created By. |  |  | Enhancement | High | HIBA HALABI | Rizwan | Failed |  | Not done.
50 | PO | When a po is set to APRV, disable all fields including signatures. When a po revision is created, previously locked fields are now editable. |  |  | Enhancement | High | HIBA HALABI | Mohsan | Fix Available
51 | PO Signatures | Notes to Supplier & Terms and Conditions are not bound by size. Dynamically bound to the same size as that in table definition. Error when going beyond the max limit. See figure. |  | Figure 10 | Bug | Medium | HIBA HALABI | Mohsan | Fix Available
52 | PO Signatures | When attempting to create a signature against an organization for which a signature template is already defined, the system throws an error, but then if the user defines terms and save, the error shown in Figure 11 is displayed. Fix the behavior so that upon seleting an organization, the system populates the defined terms for user to update. |  | Figure 11 | Bug | Medium | HIBA HALABI | Mohsan | Fix Available
53 | database tables | Rename the below: 1- ProjectPOSignature to POSignature 2- A_ProjectPOSignatures to A_POSignature 3- ProjectPOSignatureTemplate to POSignatureTemplate 4- A_ProjectPOSignatureTemplate to A_POSignatureTemplare |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Fix Available
54 | PO Signatures | None of the actions are audited! |  |  | Bug | High | HIBA HALABI | Mohsan | Fix Available
55 | PO Signatures | 1- When accessing any page, remove any previously displayed message. 2- For any page in POSignatures, when clicking on SAVE maintain the same page, and do not redirect the user to the first page. |  |  | Bug | High | HIBA HALABI | Mohsan | Fix Available
56 | PO Signatures | When attempting to create a signature using the same order no which already exists, display error from SS_Messages table. Encode it as A signature is defined with the same order number. Duplicate value detected. See figure 12. |  | Figure 12 | Bug | Low | HIBA HALABI | Mohsan | Fix Available
57 | PO Signatures | The PO Signatures are defined at the level of ORG not PROJECT. Thus no employee should be associated to the signature! Check figure 13 for more details. |  | Figure 13 | Bug | High | HIBA HALABI | Mohsan | Fix Available
58 | Project Team Members | Rename ProjectTeamMember to ProjectMembers Rename A_ProjectTeamMember to A_ProjectMembers Remove CreatedBy/CreationDate from audit table. Delete function is not working |  |  | Bug | High | HIBA HALABI | Mohsan | Fix Available
59 | POLINE | Saving POLINE returns error. See figure 14. Make sure delete/edit/create are all working successfully. |  | Figure 14 | Bug | High | HIBA HALABI | Mohsan | Fix Available
60 | POLINE | When Tax Exempt is true, Tax code & Tax should become disabled. When Tax Exempt is false, Tax Code/Tax should become editable. |  |  | Bug | Medium | HIBA HALABI | Mohsan | Fix Available
61 | POLINE | When Quantity/Rate/Line Cost is updated from the expanded panel (not from grid line iteself), the encoded formulas are not working. |  |  | Bug | High | HIBA HALABI | Rizwan | Failed |  |  | See related anomaly 67
62 | PO | Buyer name is saving buyer code, instead of name. Also buyer name should be reflected everywhere in the application where buyer is referenced. |  |  | Bug | Medium | HIBA HALABI | Mohsan | Fix Available
63 | PO | In PO, if user navigates to POLINE page, then back to PO Header page, the project search pop-up does not work. |  |  | Bug | High | HIBA HALABI | Mohsan | Cancelled |  |  | Cannot be reproduced
64 | PO | In Home page/Tasks, page is showing [you have no pending assignments] when there exists pending Purcahse orders. |  | Figure 15 | Bug | Low | HIBA HALABI | Mohsan | Fix Available |  | Already explain you, we still didn't define the permission on assigment dashboard page
65 | PO | In Pending Pos view (in Tasks page), the PONUM is showing Draft insteaf of reflecting the actual PO number. |  |  | Bug | Medium | HIBA HALABI | Mohsan | Fix Available
66 | PO | When clicking on Tax Exempt checkbox, then clicking Save, the value is not saving in the database. |  |  | Bug | Medium | HIBA HALABI | Rizwan | Open
67 | PO | POLINE Requested By field should populate values from vw_employee_table just like Buyer. Save code only. |  |  | Bug | Medium | HIBA HALABI | Mohsan | Fix Available
68 | POLINE | When deleting a POLINE, if the POLINE is line is not in the database, then delete it; otherwise, (to avoid confusion with line numbers) do not delete the item, but strikeout the line, and change the icon to the undo icon. Mimic the behavior captured in figure 17 If user clicks on the undo icon, the strikeout should disappear. - A user cannot reference a line number if it exists in the database. - Duplicate lines numbers in temp table should not be allowed. - When adding a new line, set POLINE number to maximum POLINE number in temp table + 1. - Upon saving, strikedout polines marked for deletion should be deleted. |  | Figure 17 | Enhancement | High | HIBA HALABI | Rizwan | Failed |  |  | On post-edit of POLINE num field, if user enters a line number which already exists return the error: "" Currently, if user enters an existing POLINE number, the system does not throw an error to end user, and ignores the user defined value, which is counter-intuitive.
69 | PO/Supplier | Replace icon 1 with icon 2 everywhere across the application. Icon 1: Icon 2: |  |  | Enhancement | Low | HIBA HALABI | Mohsan | Passed
70 | POLINE | When entering Tax Code manually, the page is returning error "Your changes are about to be discarded". Fix this behavior. |  |  | Bug | High | HIBA HALABI | Mohsan | Fix Available
71 | PO | Add field PRETAXTOTAL to PO table. Bind PRETAXTOTAL to the corresponding field in PO Costs Bind TOTALTAX to the the corresponding field |  |  | Bug | Medium | HIBA HALABI | Mohsan | Fix Available
72 | POLINE | Upon loading POLINE ITEM details, check receipt status from FIRMS.FIBCONSO.dbo.PORECEIVING against PONUM and POLINENUM (not POLINEID) - If RECEIPTSTATUS = COMPLETE, check Receipts Completed checkbox. - Received Cost should be retrieved from FIRMS.FIBCONSO.dbo.PORECEIVING.REMAININGQTY | Coordinate with Sabir for retrieving details on the view. 055-860 9745 |  | Enhancement | Medium | HIBA HALABI | Rizwan | Open
73 | PO | When loading PO line details, check the RECEIPTSTATUS of that particular line from FIRMS.FIBCONSO.dbo.PORECEIVING against PONUM and POLINENUM (not POLINEID) If Receipt Status is not NONE (i.e. receiving has been made on the specific POLINE), then POLINE should be entirely disabled (except for quantity). | Modify procedures. Do not hardcode in the code iteself. |  | Enhancement | High | HIBA HALABI | Rizwan | Open
74 | PO | Add Receipt Status to PO page |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Open
75 | POLINE | Upon approving a PO, check if the revised quantity is less than the received quantity. For every POLINEID, validate the ORDERQTY against FIRMS.FIBCONSO.dbo.PORECEIVING.RECEIVEDQTY for the same POLINEID. Otherwise, throw the error in Figure 18. Encode the error in SS_Messages/parametrized. |  |  | Enhancement | High | HIBA HALABI | Rizwan | Open
76 | POLINE | Costs & Quantities are not consistently being refreshed in grid when updated directly from the expanded panel. This is happening on specific scenario. To reproduce: Open PO 12023. Go to POLINE 1. Expand the line. Update the Quantity from 15 to 16 for exmaple -> The value does not get updated in the grid. See figure 19 |  | Figure 19 | Bug | Medium | HIBA HALABI | Rizwan | Open |  |  | Costs/Quantity only updated when creating a new POLINE. To reproduce the issue, open any PO. Expand POLINE 1. Update any of Line Cost/Quantity/Unit Cost, values do not refresh.
77 | POLINE | Upon updating ANY field in POLINE expanded panel, if user attempts to navigate away from the page before saving (system detected a change which is about to get discarded) return warning. |  |  | Bug | Medium | HIBA HALABI | Mohsan | Open
78 | PO | When PO page is disabled, disabled fields should not be edited. Search icons should be disabled for user click. |  |  | Bug | High | HIBA HALABI | Mohsan | Open
79 | POLINE | Bind all field sizes in POLINE to that defined in database. Binding should be dynamic not static. |  |  | Bug | High | HIBA HALABI | Mohsan | Open
80 | POLINE | In POLINE table, ITEMNUM, MODELNUM, REQUESTEDBYCODE, MANUFACTURER, REMARK, TAXCODE should be nullified if not defined and not set to an empty string |  |  | Bug | Medium | HIBA HALABI | Rizwan | Open
81 | POLINE | 1- Upon saving a POLINE, the REQUESTEDBYNAME is not being populated. 2- Supplier Ref No is not being read from DB and displayed on page. Field name: CATALOGCODE 3- Drop fields ENTERDATE & ENTEREDBY |  |  | Bug | Medium | HIBA HALABI | Rizwan | Open
82 | POLINE | If PO Status = 'APRV' OR 'CANC' OR 'CLOS' OR 'REVISD' 1- Clicking on Add New Line in POLINE should return the below error: Lines can only be added to a purchase order with a status of PNDREV, DRAFT 2- Paste button should be hidden | Error to be encoded in SS_Messages |  | Bug | High | HIBA HALABI | Rizwan | Open
83 | POLINE | Upon attempting to delete a POLINE, apply the below validations IN ORDER: 1- If PO Status = 'APRV' OR 'CANC' OR 'CLOS' OR 'REVISD' "Clicking on delete icon should return the following error: - Can only delete line if status is Draft" 2- If receiving has occurred on POLINE, return error: "You cannot delete a purchase order line against which receipts have taken place". This can be achieved by validating the POLINE against PORECEIVING_VW.RECEIVEDQTY | Error to be encoded in SS_Messages |  | Bug | High | HIBA HALABI | Rizwan | Open
84 | POLINE | Entered By and Entered Date are not properly reflected on POLINE. Also, rename the fields as shown in Figure 21 |  | Figure 20 | Bug | Low | HIBA HALABI | Rizwan | Open
85 | Contracts | Do the below changes to contracts: 1- Add the below new fields: CONTRACTNUM number Currency (same as in PO) Buyer (same as in PO) 2- Redesign the Contracts Header page, as shown in figure 21 3- If Contract Type = Amendment Order, display field Master Contract under Contract Type. Hide and nullify otherwise. Mandatory if Contract type = Amendment Order. See figure 22. 4- Master Contract is locked for editing. User should select the master contract from the list. Do not show cancelled contracts |  | Figure 21, Figure 22 | Enhancement | High | HIBA HALABI | Mohsan | Fix Available
86 | POLINE | Drop the following fields from POLINE table: RECEIVEDQTY, RECEIVEDUNITCOST, RECEIVEDTOTALCOST, REJECTEDQTY, ENTERDATE, ENTERBY, REQUESTEDDELIVERYDATE, CATEGORY |  |  | Enhancement | Medium | HIBA HALABI | Mohsan | Fix Available
87 | POLINE | Upon saving a POLINE without any changes to POLINE, the system is considering polines to be updated, and is reflected in the audit. When no change should occur on the database as no changes have taken place. On the contracy changes to PO are not done, no record stored in a_po which is the expected behavior. Critical. | To reproduce, open any PO, click on save without undergoing any change. The system will update the audit details of POLINE. select * from fsppo.dbo.A_POLINE where PONUM = '12024' and POREVISION = '0' AND POLINENUM = '2' |  | Bug | Very High | HIBA HALABI | Rizwan | Open
88 | Print PO | When printing a PO, check if below field values is not empty or null. And accordingly dynamically amend to POLINE |  |  | Enhancement | High | HIBA HALABI | Mohsan | Fix Available
89 | POLINE | Update design of POLINE grid by adding a header to grid as shown in figure 23. |  | Figure 23 | Enhancement | High | HIBA HALABI | Rizwan | Open
90 | POLINE | Quantity, Unit Price, and Total Price should accept numbers only. This is important to avoid weird behavior when using Paste functionality. See figure 24 |  | Figure 24 | Bug | High | HIBA HALABI | Rizwan | Open
91 | PO/POLINE | System should allow user to save PO without the below details if PO status = DRAFT. 1- Vendor ID/Vendor Name 2- POLINE Unit Price, Quantity, Line Cost 3- Supplier Contact Full name, position, and mobile However, upon changing status to APRV, execute the below validations: 1- PO Vendor should be selected. Otherwise throw error: "Could not change PO {{PONUM}} status to APRV. A vendor must be specified to approve this purchase order." 2- If POLINE Type = ITEM, then Quantity, Unit Price, UOM, and Line Cost are mandatory. Otherwise: return error: "Could not change PO {{PONUM}} status to APRV. A Quantity, UOM, Unit Price is required on line {{POLINENUM}}. 3- Supplier Contact Name, Position, Mobile should be selected. Otherwise, throw error: "Could not change PO {{PONUM}} status to APRV. Supplier contact name, position, and mobile are required." | Encode the errors in SS_Messages |  | Enhancement | Medium | HIBA HALABI | Rizwan | Open

## Figures
Figure 1
Figure 2
Figure 3
Figure 4
Figure 5
Figure 6
Figure 7
Figure 8
Figure 9
Figure 10
Figure 11
Figure 12
Figure 13
Figure 14
Figure 15
Figure 16
Figure 17
Figure 18
Figure 19
Figure 20
Figure 21
Figure 22
Figure 23
Figure 24

## POLINE fields
Bind to POLINE field
PONUM NOT NULL VARCHAR2(8) | x
ITEMNUM VARCHAR2(30) |  | ITEM (from ITEMMASTER.ITEMCODE)
MODELNUM VARCHAR2(14)
CATALOGCODE VARCHAR2(30) |  | Supplier Reference number
ORDERQTY NUMBER(15,2) | x
ORDERUNIT VARCHAR2(8) | x
UNITCOST NUMBER(10,2) | x
RECEIVEDQTY NUMBER(15,2) |  | Quantity Received
RECEIVEDUNITCOST NUMBER(10,2) |  | delete from db
RECEIVEDTOTALCOST NOT NULL NUMBER(10,2) |  | =UNITCOST x RECEIVEDTOTALCOST
REJECTEDQTY NOT NULL NUMBER(15,2) |  | delete from db
ENTERDATE NOT NULL DATE | x
ENTERBY NOT NULL VARCHAR2(30) | x | userid of user creating the record.
DESCRIPTION VARCHAR2(100) | x | ITEM description
REQUESTEDBY VARCHAR2(30) |  | Requested By
REQDELIVERYDATE DATE |  | delete from db
POLINENUM NOT NULL NUMBER | x | LINE
LINECOST NOT NULL NUMBER(10,2) | x
BRAND VARCHAR2(20) |  | delete from db
CATEGORY VARCHAR2(16) |  | delete from db
REMARK VARCHAR2(100)
POLINEID NOT NULL NUMBER |  | Auto-generated identifier
LINETYPE NOT NULL VARCHAR2(15) | x | LINE type
ROWSTAMP NOT NULL VARCHAR2(40) | x
TAXCODE VARCHAR2(5) |  | tax code
TAXTOTAL NUMBER(10,2) |  | tax
TAXED NOT NULL BIT |  | Tax exempted
COSTCODE | x | check with Sabir for field type def.
MANUFACTURER VARCHAR2(20) |  | Manufacturer

## ORG
1 | fibrex | GRC
2 | highland | HL
3 | contracting | CON
4 | alum | ALUM
5 | kitch | JOI
6 | mep | MEP
7 | readymix | RMD
8 | precast | PC
9 | water | WD
10 | podium
11 | landscape | LAN
12 | waterproof | WPD
13 | buildmat
14 | post
15 | toledo
16 | fibrexho | HO
17 | plant | PLA
18 | facilities | FMD | Facilities Management Division
20 | FibConso
21 | fibmaint
22 | taylor
23 | fibqatar
24 | fibfcg
25 | fibgrc
26 | fibdubai | CDXB
27 | fibfujaira | CFUJ
28 | fibrexsidential
29 | bayshield
90 | tmpFibConso
94 | tmpfacilities
95 | tmpmep
96 | tmpalum
97 | tmpCont
98 | tmpfibrex
99 | tmpfibrexho2
100 | tmpfibrexhoHR
101 | fibrexhotst
999 | ADMIN

## Currency
Currency | Code
UAE Dirham | AED
Afghani | AFN
Lek | ALL
Armenian Dram | AMD
Netherlands Antillean Guilder | ANG
Kwanza | AOA
Argentine Peso | ARS
Australian Dollar | AUD
Aruban Florin | AWG
Azerbaijanian Manat | AZN
Convertible Mark | BAM
Barbados Dollar | BBD
Taka | BDT
Bulgarian Lev | BGN
Bahraini Dinar | BHD
Burundi Franc | BIF
Bermudian Dollar | BMD
Brunei Dollar | BND
Boliviano | BOB
Mvdol | BOV
Brazilian Real | BRL
Bahamian Dollar | BSD
Ngultrum | BTN
Pula | BWP
Belarussian Ruble | BYR
Belize Dollar | BZD
Canadian Dollar | CAD
Congolese Franc | CDF
WIR Euro | CHE
Swiss Franc | CHF
Swiss Franc | CHF
WIR Franc | CHW
Unidad de Fomento | CLF
Chilean Peso | CLP
Yuan Renminbi | CNY
Colombian Peso | COP
Unidad de Valor Real | COU
Costa Rican Colon | CRC
Peso Convertible | CUC
Cuban Peso | CUP
Cabo Verde Escudo | CVE
Czech Koruna | CZK
Djibouti Franc | DJF
Danish Krone | DKK
Dominican Peso | DOP
Algerian Dinar | DZD
Egyptian Pound | EGP
Nakfa | ERN
Ethiopian Birr | ETB
Euro | EUR
Fiji Dollar | FJD
Falkland Islands Pound | FKP
Pound Sterling | GBP
Lari | GEL
Ghana Cedi | GHS
Gibraltar Pound | GIP
Dalasi | GMD
Guinea Franc | GNF
Quetzal | GTQ
Guyana Dollar | GYD
Hong Kong Dollar | HKD
Lempira | HNL
Kuna | HRK
Gourde | HTG
Forint | HUF
Rupiah | IDR
New Israeli Sheqel | ILS
Indian Rupee | INR
Iraqi Dinar | IQD
Iranian Rial | IRR
Iceland Krona | ISK
Jamaican Dollar | JMD
Jordanian Dinar | JOD
Yen | JPY
Kenyan Shilling | KES
Som | KGS
Riel | KHR
Comoro Franc | KMF
North Korean Won | KPW
Won | KRW
Kuwaiti Dinar | KWD
Cayman Islands Dollar | KYD
Tenge | KZT
Kip | LAK
Lebanese Pound | LBP
Sri Lanka Rupee | LKR
Liberian Dollar | LRD
Loti | LSL
Libyan Dinar | LYD
Moroccan Dirham | MAD
Moroccan Dirham | MAD
Moldovan Leu | MDL
Malagasy Ariary | MGA
Denar | MKD
Kyat | MMK
Tugrik | MNT
Pataca | MOP
Ouguiya | MRO
Mauritius Rupee | MUR
Rufiyaa | MVR
Kwacha | MWK
Mexican Peso | MXN
Mexican Unidad de Inversion (UDI) | MXV
Malaysian Ringgit | MYR
Mozambique Metical | MZN
Namibia Dollar | NAD
Naira | NGN
Cordoba Oro | NIO
Norwegian Krone | NOK
Nepalese Rupee | NPR
New Zealand Dollar | NZD
Rial Omani | OMR
Balboa | PAB
Nuevo Sol | PEN
Kina | PGK
Philippine Peso | PHP
Pakistan Rupee | PKR
Zloty | PLN
Guarani | PYG
Qatari Rial | QAR
Romanian Leu | RON
Serbian Dinar | RSD
Russian Ruble | RUB
Rwanda Franc | RWF
Saudi Riyal | SAR
Solomon Islands Dollar | SBD
Seychelles Rupee | SCR
Sudanese Pound | SDG
Swedish Krona | SEK
Singapore Dollar | SGD
Saint Helena Pound | SHP
Leone | SLL
Somali Shilling | SOS
Surinam Dollar | SRD
South Sudanese Pound | SSP
Dobra | STD
El Salvador Colon | SVC
Syrian Pound | SYP
Lilangeni | SZL
Baht | THB
Somoni | TJS
Turkmenistan New Manat | TMT
Tunisian Dinar | TND
Pa’anga | TOP
Turkish Lira | TRY
Trinidad and Tobago Dollar | TTD
New Taiwan Dollar | TWD
Tanzanian Shilling | TZS
Hryvnia | UAH
Uganda Shilling | UGX
US Dollar | USD
Uruguay Peso en Unidades Indexadas | UYI
Peso Uruguayo | UYU
Uzbekistan Sum | UZS
Bolivar | VEF
Dong | VND
Vatu | VUV
Tala | WST
CFA Franc BEAC | XAF
East Caribbean Dollar | XCD
CFA Franc BCEAO | XOF
CFP Franc | XPF
Sucre | XSU
ADB Unit of Account | XUA
Yemeni Rial | YER
Rand | ZAR
Zambian Kwacha | ZMW
Zimbabwe Dollar | ZWL

## Permissions
CONTRACT_MGR
CONTRACT_VW

## Merging Tips
System | DB Object | Tip
FIRSM | depm_master | depm_allow_po_rls should be set to '1' for all projects for which creating PO is allowed. Remaining should have the field set to '0' not NULL.

## Sheet2 (hidden)
Type | Priority | Status
Bug | Low | Open
Regression | Medium | Fix Available
Enhancement | High | Failed
New Development | Very High | Passed
Missing Function |  | Cannot Reproduce
Cancelled
Postponed