## List
# | Page | Description | Reproduction Scenario | Referred Figures | Type | Priority | Tester | Developer | Status | ETA | Developer's Comments | Tester's Comments
1 | frmCreateNewPurchaseOrder | Remove asterisk from PO Number, Revision, Status and Status Date |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
2 | frmCreateNewPurchaseOrder | When selecting the organization, the ORGNAME should show on the form and not the code. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  | only did update purchase order, just to verify. If it is ok for you, I will implment on rest of the pages | It creation mode, it works fine. When opening an existing PO, it displays the code and not ORGNAME.
3 | frmCreateNewPurchaseOrder | Project is not being loaded according to the selected Organization. When selected, show the project code on the form. Disable Project until ORG is defined. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Keep select option in dialog box. Value should not be loaded when clicking ENTER. Issue with loading the projects when the organization name is updated. Make sure to refresh the projects when updating the organization.
4 | frmCreateNewPurchaseOrder | For all BUYER fields in the application, the dialog should only show the usernames who have security group = BUYER. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
5 | PO,POTEMPLATE | For all fields which have search icons associated to them, VALIDATE EVERY USER INPUT on both SAVE and field exist. If user enters any value which does not belong to the list, the system should highlight the field in red. Validation should be carried out on SAVE as well. Example: Invalid buyer name/Invalid Project/Invalid Organization |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available |  |  | 1- Validation not carried out on SAVE. Server error shows. Test it for every single field which requires validation. 2- Contract ID not validated. 3- Same validation to be carried out for PO Tempalate on field change and save.
6 | PO table | Increase ORIGINALPONUM to 50 characters |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
7 | frmCreateNewPurchaseOrder | Vendor Date and Quotation Date are not mandatory. By default, ORDERDATE = curdate. The remaining dates should not be defaulted. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed |  |  | Vendor Date and Quotation Date should NOT be mandatory. Currently they are mandatory. Remove the asterisk. Order Date and Required Date are mandatory.
8 | frmCreateNewPurchaseOrder | Cannot navigate to next page from Select Supplier dialog box. System error returned. See figure 1. |  | Figure 1 | Bug | Very High | Hiba HALABI | Mohsan | Cannot Reproduce
9 | frmCreateNewPurchaseOrder | Vendor Name should be automatically populated when selecting Vendor ID. This field is disabled (not enabled for editing). When Vendor ID is updated, Vendor Name should be also updated. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
10 | frmCreateNewPurchaseOrder | PO Type dialog returns no results. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
11 | PO | 1- Revision comments is always disabled, and bounded to field po.REVCOMMENTS. (also remove Revision History defaulted value) 2- PO number is bounded to POREF and not PONUM. If null, insert Draft. 3- PO description length should be bounded to database field length. Make sure all remaining fields are bounded to the database data length. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Remove Description from being the defaulted value for PO Description. Remove organization defaulted value.
12 | POLINE | Auto-update of poline fields when updating LINEQTY, UNITPRICE, and LINECOST. |  |  | Bug | Low | Hiba HALABI | Mohsan | Fix Available |  |  | -If Quantity is updated, and Unit Cost is defined, update LINECOST. - If Quantity is updated, and Unit Cost is null or empty or zero, and LINECOST is defined-> update Unit Cost - If Unit Cost is updated, and Quantity is defined, update LINECOST. - If Unit Cost is updated, and Quantity is null or empty or zero, and LINE COST is defined -> update Quantity. - If LINECOST is updated, and Quantity is defined -> update Unit Cost. - If LINECOST is updated, and Quantity is null or empty or zero, and UNIT COST is defined -> update Quantity.
13 | POLINE | Add Supplier Reference to POLINE grid. (shrink the costcode column width) Title: Supplier Ref. Location: After Line Type Bind to db field: CATALOGCODE |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  | Update the SP as well, PO_ADDPOLIne PO_EditPOLIne PO_deletePoline
14 | POLINE | Delete, insert, and edit not working in certain cases. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available |  | There was a problem is updating the valus in session, it was fixed | - When deleting a row, and then inserting new row, POLINENUM can be equal to the value of the old row (since it was already deleted from table before new row was inserted). - A row is marked as UPDATED even though no update it done. Check the below query: select * from fsppo.dbo.A_POLINE where PONUM = '1019' and POREVISION = '0' and POLINEID = '46' Could be the page is not being refreshed, and it is still marked as update from the previous page save.
15 | Search PO | Project is null in results. Return Project Name and OrgName (not code). Enter space between first and last name for buyer. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
16 | PO | Add audit information to end of PO page, just like Registration page. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  | In PO Table, If vender name is less then 50 it, expect this, if vender name legnth is more then 50, it give me an error, string and binary data. Even in table and SP we define is vendername is 100
17 | A_PO, A_POLINE | Audittimestamp should be datetime and not date only. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
18 | POLINE | clicking TAB after QTY, and attempting to type does not work. Issue with UOM. TAB does not work after QTY field. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
19 | POLINE | When a record cannot be inserted/edited in POLINE and procedure raises error, the error is not being reflected on application to the user, and the changes are discarded. | To reproduce, open a PO, and remove the QTY, UNITPRICE, and TOTALLINECOST from a given POLINE where LINETYPE = ITEM. Click save. The record is not saved, changes are discarded without returning to the user. |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Server error.
20 | Attachments | Error when trying to add a valid attachment |  | Figure 2 | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Distorted dialog box. Take long time to attach and result in error.
21 | POLINE | Do not auto update SUBCOST and TOTALCOST in POLINE header. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available |  | updated issue fixed | Call PO_CalculatePOTotalAmount upon saving. Do NOT auto-update anywhere in the code.
22 | Revise PO | Revise PO is not working. It should start by calling the procedure PO_GETNEXPOREV. If it returned an error, then the dialogbox should NOT show, and the same error should be returned to the user. Otherwise, display the dialog box showing in Revision, the returned revision number from procedure output. | To reproduce, go to Search PO, open PO 1006. Click Revise PO, the dialog box shows with wrong information. On the contrary, if you call the procedure, it returns an error! declare @nextrev smallint exec fsppo.dbo.PO_GetNextPORev '1006', '0', @OUTPUTNEXTREV = @nextrev OUTPUT print (@nextrev) |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  | I updated SP, Change in RaiseError, after that, I update in the code
23 | Change Status | Clicking on Change Status returns an error. | To reproduce, open registration #1006. Click on Change Status. It will return an error. |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
24 | Print PO | print PO should open in a NEW TAB. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
25 | View Revision History | Clicking on View Revision History returns an error. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
26 | PO | Opening any PO returns an error. See figure 3. |  | Figure 3 | Bug | Very High | Hiba HALABI | Mohsan | Passed
27 | New Contract | Upon creating a new contract, clicking on Organization and attempting to select a given value does not work |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
28 | New Contract | Upon creating a new contract and filling into all values, clicking save returns no action! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Failed |  |  | Clicking on Save should remain on the same page where user can edit the underlying contract with no need to go back to Search Contract page. Mimic same behavior as Purhase Order.
29 | Load PO Template | Dialog box should show the below columns in order: - Template Name - Organization (Name) - project Name - Vendor Name - Created By No filter should be available on 'select' option. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Filter should be available on first column (i.e. Select) - Vendor Name search filter is not working.
30 | Search PO Templates | Filters & grid output. Template Name Template Description Organization (filter) Project(filter) Vendor(filter) Created by (filter) Created after (calender) in the output, the link should be on Template ID (first column) which is the same behavior for Registration, Supplier, and PO. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | - First column should be template ID. - By filter, I mean add them as filter in the search criteria and not in the grid. Behavior should be same like all other search pages.
31 | Po Templates | Vendor ID/Vendor Name is not mandatory. Mandatory information are: Organization & Buyer |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available |  |  | Project is mandatory. Type is not mandatory.
32 | PO Templates | Vendor ID/Vendor Name should be disabled and attain same behavior like PO. Unable to select a Vendor ID from dialog box. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | Create Contract is not working. Clicking on SAVE does not result in any update on the databae, and does not return any error to the user.
33 | PO Templates | Add audit information to the end of the PO Template Page. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  |  | Create Contract is not working. Clicking on SAVE does not result in any update on the databae, and does not return any error to the user.
34 | PO Templates | Add Template ID and Template Owner in the Templates Information section. Rename Templates Information to Template Header. Template Owner = Logged in user. The Template ID and Template owner will show upon saving, and when editing an existing template. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  |  | Create Contract is not working. Clicking on SAVE does not result in any update on the databae, and does not return any error to the user.
35 | PO/PoTemplates | Disable vendor ID from PO/Edit PO/PO Templates/Edit Po Template pages |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
36 | Dialog boxes with filters | % should be accepted by all filters in dialog boxes. See Figure |  | Figure 4 | Enhancement | High | Hiba HALABI | Mohsan | Open
37 |  | Change datatype of ORDERTYPE, REQUIREDATE, VENDORDATE, and QUOTATIONDATE to DATE and not DATETIME in all relevant tables and procedures. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
38 | PO | - When a purchase order is successfully created, return a confirmation message to be referred to from SS_MESSAGES. - When PO change Status is successfully applied, return confirmation message to user: Status successfully updated. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
39 | Errors | When an error is shown for any reason, if user removes the error, and apply any operation on the page, the old error is reshowing. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
40 | PO print | If only one supplier is defined, the grid should show only one line in Supplier Details. If VENDORATTN2NAME is null, show one row. Else, show 2 rows. |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Open
41 | PO | Upon saving a PO (creation or edit mode), check whether the underlying Vendor is blacklisted. If supplier status blacklisted, return warning: The selected vendor %vendorname is blacklisted. Encode in SS_Messages |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available |  | only active supplier is load in the popup list. | All suppliers should be loaded regardless of the status. Show warning as specified.
42 | PO | The below fields should not be mandatory (creation/update mode): Supplier Contact 1 Fax, Supplier Contact 1 Email, Supplier Contact 1 Phone |  |  | Enhancement | High | Hiba HALABI | Mohsan | Fix Available |  |  | Asterisks missing on mandatory fields.
43 | PO, POTEMPLATE | When a field is highlighted in red, once the user type into it, the highlight should be removed. | To reproduce, create a PO without defining the Supplier Contact Information. Click SAVE. Mandatory fields are highlighted in red. Once defined, the border should be removed, but it still persists. |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available |  |  | - Not done for PO Project. - Not done for all Organization, Project, and Type in PO Template.
44 | Pending PO Assignments | - Increase PO Ref. Increase Vendor. Decrease Project. - Order by descending order of Creation Date. - In underlying query, add condition: where buyer = loggedin user. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
45 | Search PO | -Organization filter should show name and not code. -Project filter should show name and not code. - In results, PO REF should be left-aligned, not center-aligned. - None of the filters are working. - Add checkbox View Revisions History, as specified in the specs for which you need to search also from POARCHIVE and POLINEARCHIVE. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
46 | Refresh PO | Refreshing the page should reload the form, and not resubmit it. - When a change is detected, the system should return warning message. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available |  | Fixed on All Pages, PO, EDIT PO, Create Templates, Edit Templates | Refreshing is not prompting the user to confirm page refresh or discard changes, when one or more fields are changed.
47 | PO | Buyer field value should show username and not first name. Validation should also be carried on username and not first name, in creation and edit modes. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
48 | POLINE | LINEQTY, LINECOST, and UNITCOST are rounding up to integers. Should be defined as numbers with 2 decimal points. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
49 | Serve Error | The application SHOULD NOT RETURN SERVER ERROR UNDER ANY CIRCUMSTANCE! Show the error on the front-end. This is a critical issue. REVIEW THE ENTIRE CODE! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Open
50 | POLINE | Error when trying to update PO grid and saving. Reference attached figure. |  | Figure 5 | Bug | Very High | Hiba HALABI | Mohsan | Passed
51 | Contact | Contracts relationship is NOT WORKING! When adding a contract and clicking on save, nothing happens! No error is returned to user, and no action is undertaken. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Open |  |  | To check with Hiba
52 | POLINE | Start with POLINENUM = 1 and not 0. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available
53 | Attachments | Update on PO Attachments is not working. The record is being discarded. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
54 | PO | When PO Status is approved, the second tab featuring POLINE grid and additional charges should all be disabled. Keep attachmets open. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
55 | PO | PO Revision comments is not reflecting PO.REVCOMMENTS field value. | To reproduce, open PO F-3-ALD001-PUR-1-2017, Rev 1. Revision comments is empty, although REVCOMMENTS in defined in PO table for the underlying PONUM and REVISION. | Figure 6 | Bug | High | Hiba HALABI | Mohsan | Fix Available
56 | PO | When changing status of PO rev > 0 to approved, application is showing successful status update, when nothing is taking place. | To reproduce, go to PONUM = 1019, Rev 1. Change Status to approved. Click Submit. It shows Status Updated successfully, but the status is still PNDREV. |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
57 | Print PO | POLINE grid not showing | To reproduce, go to PONUM = 1019, rev 1 and print PO. Grid is not showing, |  | Regression | Very High | Hiba HALABI | Mohsan | Fix Available
58 | PO | When entering valid organization directly without prompt, then selecting from prompt project, then entering valid type without promot, then entering any values for remaining fields -> selecting a vendor does not populate its details in the form. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
59 | Search PO | - Do not carry validations on Search PO search fields: Organization, Project, Type, and Buyer. % sign should be accepted, and running successfully. - Clicking on Enter should be equivelant to clicking on earch button. Currently error shown in Figure 7 is returned. There is no minimal selection on criteria. |  | Figure 7 | Bug | High | Hiba HALABI | Mohsan | Fix Available
60 | Search PO | - None of the fields in the tabs are working! POLINE, DATES, and Reference documents. - Return error if value in dates fields is not a DATE. Error is already encoded in SS_MESSAGES |  |  | Bug | High | Hiba HALABI | Mohsan | Open |  |  | Hiba to create procedure
61 | Search PO | Search Revisions History: when selected, need to search as well from POLINEARCHIVE and POARCHIVE |  |  | BUg | High | Hiba HALABI | Mohsan | Open |  |  | Hiba to create procedure
62 | POLINE | Description and TOTALCOST are mandatory fields. Validate on save. Description cannot be empty string or null (after trim). Totalcost should not be zero or empty string or null. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
63 | POLINE | Validate UNITCOST, QTY, LINECOST, Less Amount, Additional Amount on fieldchange/fieldexist. It should be decimal values ONLY. i.e. attempt to convert the value to number (10,2). If it resulted in error, return error to the user immediately. Save validation should be carried on save. Should reference one record in SS_MESSAGES with field name as parameter. |  |  | Bug | High | Hiba HALABI | Mohsan | Open

## Figures
Figure 1
Figure 2
Figure 3
Figure 4
Figure 5
Figure 6
Figure 7

## POLINE
Action 1 | Action 2 | Status
NULL | Insert | not working for line 2 and beyond
Insert | Edit | Not working
NULL | Edit | working
NULL | Delete | working

## Sheet2 (hidden)
Type | Priority | Status
Bug | Low | Open
Regression | Medium | Fix Available
Enhancement | High | Failed
New Development | Very High | Passed
Missing Function |  | Cannot Reproduce
Cancelled