## List
# | Page | Description | Reproduction Scenario | Referred Figures | Type | Priority | Tester | Developer | Status | ETA | Developer's Comments | Tester's Comments
1 | General | Session should expire in 30 minutes |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Open |  |  | Add a message.
2 | FrmChangePassword | Upon changing the password, no message is being generated, and the application just redirects the user to the login page. Add message: Password has been changed successfully. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
3 | FrmChangePassword | Upon reseting the password, the system is accepting any new password irrespective of any condition. The below conditions captured in the specs document, section 6.1 are not implemented. | For username hiba, the password was successully changed to 'A'. The conditions for new password are not implemented. See conditions from specs, section 6.1. | Figure 1 | Bug | High | Hiba HALABI | Mohsan | Passed
4 | FrmChangePassword | No error is returned when the passwords New Password and Confirm New Password do not match. In fact, the password is being successfully updated to New Password. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
5 | Logout | Loging out return File Not Found page. See Figure 2 |  | Figure 2 | Bug | Medium | Hiba HALABI | Mohsan | Passed
6 | MgmDashboard > Tasks | The Tasks panel shoud reflect the number of entries corresponding to each element |  | Figure 3 | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Incorrect number indicted for expired trade licenses and Internal Supplier Registrations.
7 | FrmRegistration | Upon clicking on SAVE, display a pop-up message Mandatory information missing. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
8 | FrmRegistration | Upon updating the Business Classification such that the License changes from Trade License to Emirates ID or vice-versa, reset the fields (empty the values). |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  |  | It is only done for the License Number, and not to issuing authority and expiry date. Second, it is only done for external supplier registration and not for the internal registration, FrmRegSupplier.
9 | FrmRegistration | Unable to save the registration. Error: String was not recognized as a valid DateTime. |  | Figure 4 | Bug | Very High | Hiba HALABI | Mohsan | Passed
10 | FrmRegistration | The Phone Number under Address is not implemented as a mandatory field. |  | Figure 5 | Bug | Low | Hiba HALABI | Mohsan | Passed
11 | FrmRegistration | No validation is made on the Company Name. |  | Figure 6 | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | Change error to Company Name already exists.
12 | MgmDashboard | From the Search Registration panel, upon clicking on Search, the page is refreshed and scrolled back to top. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
13 | MgmDashboard > Search Registrations | Incorrect search results upon filtering on supplier address from Search Registrations. |  | Figure 7 | Bug | Medium | Hiba HALABI | Mohsan | Passed
14 | MgmDashboard > Search Suppliers | Incorrect search results upon filtering on supplier address from Search Suppliers. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
15 | frmApprovedSupReg | The transitions between the different statuses are not implemented. For example, when the status is Pending Approval, the only allowable statuses are Approved, Rejected, and Supplier to Provide Details. The status Re-opened should not be present. Figure 8 capture the allowable transitions. |  | Figure 8 | Enhancement | High | Hiba HALABI | Mohsan | Passed
16 | frmApprovedSupReg | The Prospective Supplier Registration page should relfect the Registration Number, Registration Status should be captured at the beginning of the page, not included within the Company Information. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
17 | frmApprovedSupReg | Once the Registration is approved, the status field should be uneditable. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed |  | Regression: cannot save the page anymore. Error upon saving the page.
18 | FrmRegistration | Company Short Name should not be mandatory |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
19 | FrmRegistration | Upon entering the Expiry Date as DD/MM/YYYY, and clicking on save, the system returns an Object Reference related error, but the system actually saves the registration in the Registration table, but does NOT save the Address in the RegSupAddress table. | To reproduce, create a registration while filling all mandatory fields correctly, and entering Expiry Date as 12/03/2016. Clicking on save returns and error, but actually saves the registration in the Registration table, but does NOT save the Address in the RegSupAddress table. Open registration 10005 from the application, the address information is empty. |  | Bug | High | Hiba HALABI | Mohsan | Passed | Change the date format into MM/dd/YYyY | Change the date format to DD-MON-YYYY | Missing fields: StatusDate in registration, statusDate in Supplier Profile, Trade License Expiry date under external registration, Expiry date in frmUpdateRegistration
20 | MgmDashboard | Add the buttons Notify All Suppliers and Register New Supplier as shown in figure 9. Clicking on Notify all opens a pop windows to send notification to the previously selected suppliers. If no supplier is selected, return error Please select suppliers to notify. CLicking on Register New Supplier opens the internal supplier registration page. |  | Figure 9 | Bug | High | Hiba HALABI | Mohsan | Passed
21 | MgmDashboard > Search Suppliers | Trade License Expires Before date does not show a calender. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
22 | MgmDashboard > Tasks | Expired Trade Licenses are not detected. | For example, upon logging into the application today 11/8/2016, the system should reflect from Tasks Panels the number of expired Trade Licenses. For example, Supplier 10000 has an expired Trade License. |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Incorrect number is displayed in the Tasks pane.
23 | MgmDashboard > Tasks | Upon clicking on any task from the task pane, if the Search filters have already been defined when the task is selected, the previously defined data is not cleared. Make sure to clear the search criteria for all tasks prior to applying the task related filters. | To reproduce, define any search criteria on Search Suppliers page on filters Company Name, Supplier Number, and Address for example. Now click on Expired Trade Licenses from the tasks pane, the Trade License Expired Before gets properly set to the current date, but the remaining filters are not cleared out. |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Failed for expired Trade Licenses.
24 | DashBoard1 | The second dashboard is not working |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
25 | FrmSupplierProfile | Upon clicking on a specific Registration from the Search Registrations page, the registration should open in the detailed form, and not the quick registration form, which includes the banking details and additional Address. Banking details and second Address are not shown. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Cancelled
26 | FrmSupplierProfile | Upon clicking on a specific Registration from the Search Registrations page, the registration should open in the detailed form including a NOTIFY button, which when selected opens a pop-up notification window to be able to send a notification. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed |  |  | Notify button is not responding!
27 | MgmDashboard > Tasks | Clicking on Re-opened Prospective Supplier Registrations does not define Registration Type to External. Missing filter. See section 7.8.4 from specs document. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Clicking on Re-opened Prospective Supplier Registrations returns an error.
28 | MgmDashboard > Tasks | Clicking on Re-opened Internal Supplier Registrations from the Task pane does not respond. See section 7.8.3. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Clicking on Re-opened Internal Supplier Registrations returns an error.
29 | MgmDashboard > Tasks | Clicking on New Internal Supplier Requests does not respond. See section 7.8.1 from specs document. |  |  | Bug | High | Hiba HALABI | Mohsan | Cancelled |  |  | No search results are dispayed
30 | MgmDashboard > Tasks | Clicking on task Supplier Profile Change Requests from the Tasks panel does not respond. See section 7.8.5 from specs document. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
31 | MgmDashboard > Search Suppliers | Remove the comma (,) from Sup Type, when there exists a single type. Use the comma to separate between two types. |  | Figure 10 | Bug | Low | Hiba HALABI | Mohsan | Passed |  |  | See figure 14. This should be done via domain table. Use the codes below and implemented it in domain ALPDomain. SUPPL --> Supplier SUB --> Subcontractor SS --> Supplier,Subcontractor In the Registration and Supplier table, store the Domain ID. In the Search Results, display the Domain Name.
32 | MgmDashboard > Search Suppliers | Use Domain Names and not Domain ID in the Search Supplier results grid. For the grid header, use full names for Supplier Number, Supplier Type. |  | Figure 10 | Enhancement | Low | Hiba HALABI | Mohsan | Passed |  |  | Use full names in header. Not corrected.
33 | Notifications | Clicking on a notification returns File or Directory not found. |  | Figure 11 | Bug | Very High | Hiba HALABI | Mohsan | Passed
34 | FrmChangePassword | - When the current password is incorrect, and the user clicks on save, the system returns error Old Password not Match. Change the error text to The current password is incorrect. Please try again. - When the New password and Confirmed Password do not match, show the error Passwords do not match (same format as above error). |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available |  |  | Upon editing the new password/reneter new password, if there is a previously red border highlighting the re-enter password field, it should be removed.
35 | FrmRegSupplier | For internal supplier registration, the phone number under Address 1 and 2 should be mandatory. Company Short Name should not be mandatory. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
36 | FrmRegSupplier, FrmRegistration | Pop-up message Mandatory Information Missing should be displayed, when a mandatory information is missing. As discussed, this should be done in addition to the highlight of fields. Not error should be assumed indirectly. Errors should be explicitly articulated to the end-user. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
37 | FrmRegSupplier | Error upon saving an internal Supplier Registration. Fixes that are done for the external supplier registration has to be implemented for the internal registration as well. |  | Figure 12 | Bug | Very High | Hiba HALABI | Mohsan | Passed
38 | frmApprovedSupReg | Error upon saving the registration page. See figure 13. |  | Figure 13 | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | Error: "Object reference not set to an instance of an object." But the record is being saved in the database, with status Approved!
39 | frmApprovedSupReg | Registration form should be READ ONLY if status is approved. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
40 | frmApprovedSupReg | Change Status should be disabled (not hidden) if the current status is set to Approved |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
41 | N/A | On every page displaying a grid, modify the display of the pages navigation as shown in figure 15. |  | figure 15 | Enhancement | Medium | Hiba HALABI | Mohsan | Open
42 | FrmRegSupplier | Upon defining Phone Number in Address, which has been previously missed, the previously highlighted red border is not removed. |  |  | Bug | Low | Hiba HALABI | Mohsan | Passed
43 | N/A | Remove isChangesUpdated from all tables in database. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
44 | N/A | For all fields in the all tables in the database, when a value is not defined, it should be reported as NULL and not an empty string. |  |  | Enhancement | Very High | Hiba HALABI | Mohsan | Passed |  |  | regSupplierAddress table is missed. Check registration 10024.
45 | Search Registrations | Clicking on Clear button does not clear the previously defined values. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
46 | Change Status | Upon clicking on Submit, the dialog box should disappear, and the registration page should be refreshed displaying the udpated status. No confirmation message is required. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
47 | Registration page | Add Notify in the list under Actions combobox, such that upon clicking on Notify, the system prompts the user to send a notification to the underlying registered user. This action does not change the status of the underlying registration. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
48 | Search Profile Change Requests | Upon clicking on Search, check if the From Date is greater than the To Date, and throw error message: "From Date cannot be greated than the To Date." |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Passed
49 | Search Profile Change Requests | The link should be for the Change Request ID and not Supplier Number. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
50 | frmManageChangeRequestApprovals | The Change Request page should load the Domain Description and not Domain Values for fields referenced in the domain table, like Supplier Type. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
51 | frmManageChangeRequestApprovals | Fields which are referenced in the Domain table should not be reflected as text fields, rather a combobox which populates the values from the Domain table, like Business Classification, Supplier Type, and Country. |  | Figure 16 | Enhancement | High | Hiba HALABI | Mohsan | Passed
52 | frmManageChangeRequestApprovals | Once the Changes are applied, the grid should become read-only and Apply and Reject buttons should be hidden. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
53 | FrmSupplierProfile | Once Update button is pushed, and the page shows Successful creation of change request, the page should become entirely disabled. Otherwise, changes can be applied. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
54 | frmChangeRequestHistory | Memo should reflect only the first 255 characters. To view the entire memo, user can click on […] link which shows a pop-up displaying the entire memo. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available
55 | frmChangeRequestDetail/frmManageChangeRequestApprovals | Attribute shows field name in the Supplier table and not the field title present in the Labels table in database. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
56 | frmChangeRequestDetail/frmManageChangeRequestApprovals | RegDocExpiryDate current value is reflected as datatime, when it should show the date only. |  | Figure 17 | Bug | Low | Hiba HALABI | Mohsan | Passed
57 | frmManageChangeRequestApprovals | Upon clicking on Reject OR Cancel, if user has modified at least one value in the page, the system should return pop-up message: "Your changes shall be discarded. Do you like to continue?" |  |  | Bug | Medium | Hiba HALABI | Mohsan | Failed |  |  | When changes are applied, the warning message is not being generated. For reproducing the test-case, go to CR #13, and change the supplier type, then click Back or Reject. The warning message is not shown.
58 | Notifications | Notification page should display From, To, Sent (Date/time), and Subject. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
59 | FrmSupplierProfile | When a Company profile is locked, show error message as alert (label): "There is a pending profile change request for this supplier. The profile remains uneditable until change request is reviewed." Check figure 18. |  | Figure 18 | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
60 | FrmSupplierProfile | When a Company profile is locked, the Update button should be disabled (not hidden). Page should show View Change Request button, which opens the underlying change request. Supplier Type checkboxes should also be disabled. |  | Figure 18 | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
61 | frmManageChangeRequestApprovals | When the Change Request is rejected, and the user fills the memo, clicking on submit does not update the CR Status to Rejected, and the page is not disabled. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
62 | FrmSupplierProfile | Mandatory fields are not checked upon updating a profile. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | Show error message. Mandatory information missing.
63 | frmManageChangeRequestApprovals | Update method should be implemented for all fields in the profile page. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
64 | FrmSupplierProfile | Upon updating a profile, if the banking method is set to bank transfer, then all remaining banking details become mandatory. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
65 | FrmSupplierProfile | View Change Request button should show only when the profile is locked. It should be hidden otherwise. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
66 | frmApprovedSupReg | When the supplier registration is approved, and the supplier gets created, 2 addresses are created in SupAddress with second address have all NULL values (even if second address is null). The second record should be created only if the secondary address is defined. |  | Figure 19 | Bug | High | Hiba HALABI | Mohsan | Passed
67 | frmApprovedSupReg | When the supplier registration is approved, and the supplier gets created, the country value is set to NULL even when the country is defined. |  |  | Regression | High | Hiba HALABI | Mohsan | Passed
68 | Change Request | After clicking on apply, the status changes to applied but in reality none of the changes has been propagated to the underlying supplier. |  |  | Regression | Very High | Hiba HALABI | Mohsan | Passed
69 | frmChangeRequestDetail | Error message when opening an existing change request: "sequence contains more than one element". | To reproduce, open change request #19. |  | Regression | Very High | Hiba HALABI | Mohsan | Passed
70 | frmInternalRegistration | Unable to save a registration, returning Mandatory Information Missing |  |  | Regression | Very High | Hiba HALABI | Mohsan | Passed
71 | frmUpdateRegistration | Missing attachments. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
72 | frmUpdateRegistration | Upon clicking on Change Status and then submitting, the page is not being refreshed (old staus is not updated). |  |  | Regression | Very High | Hiba HALABI | Mohsan | Passed
73 | frmUpdateRegistration | Mandatory information are not being checked when updating a registration. | To reproduce, open any registration, nullify any mandatory field, and click on save. The changes are being saved successfully. |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
74 | frmUpdateRegistration | View Status History is not working. Pop up window is empty. |  |  | Regression | Very High | Hiba HALABI | Mohsan | Passed
75 | Notify | Disbale Submit button when clicked; otherwise, multiple notifications can be sent by mistakenly clicking the submit button multiple times. Seee attached snapshot. |  | Figure 20 | Bug | High | Hiba HALABI | Mohsan | Fix Available
76 | frmInternalRegistration | Fix the alignments on frmInternalRegistration page |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Passed
77 | FrmSupplierProfile | Upon updating a profile, and clicking on View Change Request, the pop-up page returns no results. |  |  | Regression | High | Hiba HALABI | Mohsan | Passed
78 | frmChangeRequestDetail | Payment Method should be reflected as drop-down under proposed value, and not a free text |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
79 | frmManageChangeRequestApprovals | Correct fields alignments. Enhance user interface. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Failed
80 | frmSearchProfileChangeRequest | Filters Date From AND Date To are not working correctly. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
81 | frmManageChangeRequestApprovals | Address 1 Fax Number & Address 2 Fax Number are not being treated when CR is applied (i.e. change is not propagated to supplier profile). Mis-identification of field. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
82 | frmManageChangeRequestApprovals | Expiry Date should show calender and not free text field. |  |  | Bug | High | Hiba HALABI | Mohsan | Failed
83 | frmSupplierGeneral | Enhance the user interface of this page. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Open
84 | frmManageChangeRequestApprovals | Upon clicking on Reject, a pop-up window should prompt the user to define the Reason for Rejection only, and not subject/message. A notification template is implemented for this event. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Open
85 | FrmSupplierProfile | When supplier status is updated, the page is not being refreshed. Old status/Status Date is maintained. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
86 | FrmSupplierProfile | When supplier status is updated to blacklisted, the supplier account associated to the blacklisted supplier should be locked. Currently, it is still active. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
87 | FrmSupplierProfile | Status Date is reflecting the supplier creation date from supplier table, and not the latest record fetched from SupplierStatusHistory table. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
88 | frmInternalRegistration | Remove Address Line 2 and Banking details sections. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
89 | frmSupplierGeneral | Add grid navigation for attachments grid and notifications as implemented for Supplier Master search. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
90 | frmInternalRegistration | Add attachments grid. |  |  | Bug | High | Hiba HALABI | Mohsan | Failed |  |  | Implemented only for external registration, and for frmSupplierGeneral
91 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | Upon clicking on Add Attachment, prompt the user for dialog box captured in Figure 21 to browse for file and specify the file title and description. Upon clicking on update button, the same dialog box is shown for editing the values/attachment. |  | Figure 21 | Enhancement | HIgh | Hiba HALABI | Mohsan | Passed
92 | FrmRegistration > Attachments | Add a new field in attachments grid, namely Visible to Supplier. - Field Type: Text-box - Field Name: Visible to Supplier - Field location: before Upload Date/Time |  |  | Enhancement | High | Hiba HALABI | Mohsan | Open
93 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | Modify the attachments grid so that the below fields appear in the following order: - File Name - Title - Description - Visible to Supplier (not available to external user) - Uploaded By - Uploaded Date/Time |  |  | Enhancement | High | Hiba HALABI | Mohsan | Fix Available
94 | FrmRegistration | When adding attachment, Uploaded By is set to GUEST. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Open
95 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | When uploading an attachment, read the file header, and check the ACTUAL file type, and not simply the file extension which can be edited. Allowable file types are: pdf, doc, docx, xls, xlsx, csv, (zip), jpg, jpeg, png, gif |  |  | Bug | Very High | Hiba HALABI | Mohsan | Open
96 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | Upon deleting a file, the reference is being deleted from the database, but not the actual file on the server. Delete the file from the server when successfully deleted from the application. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Open
97 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | File Title and File Description fields for attachment are not mandatory. When no title is specified, then the title is the actual file name. e.g. if user upload my trade license.pdf and specifies no title for the attachment, then the default title is "my trade license.pdf" |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Open
98 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | Upon clicking on add attachment, if a file name is defined, and user clicks on Submit without selecting a file, throw an error "No attachments has been specified. Please select a file to attach." |  |  | Bug | Medium | Hiba HALABI | Mohsan | Open
99 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | Upon successful attachment uploading, show message: Attachment title has been added successfully but not committed; it would be committed when you commit the rest of the current transaction. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Open
100 | frmInternalRegistration/ frmSupplierGeneral/ FrmRegistration | Upon deleting an attachment, show warning message: "Are you sure you want to delete the attachment <<File title>> for this record? |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Open
101 | frmSearchSupplier/frmSearchProfileChangeRequest/frmInternalRegistration | Trade License Expires Before, CR Date From, CR Date To, Expiry Date fields should not be editable. Backgroud should be white. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Open
102 | frmSupplierGeneral | Search Attachments and Search Notifications not working. |  |  | Bug | High | Hiba HALABI | Mohsan | Open
103 | frmSupplierGeneral > Attachments | Upon clicking on Show more search options, display fields: Uploaded By, From Date (calender), To Date (calender), and visible to supplier checkbox. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Open
104 | frmSupplierGeneral > Notifications | Upon clicking on Show more search options, display fields: Sent By, From Date (calender), To Date (calender). |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Open

## Figures
Figure 1
Figure 2
Figure 3
Figure 4
Figure 5
Figure 6
Figure 7
Figure 8
Figure 9
Figure 10
Figure 11
Figure 12
Figure 13
Figure 14
Figure 15
Figure 16
Figure 17
Figure 18
Figure 19
Figure 20
Figure 21

## Messages
Action | Page | Event | Message
Change Text | FrmRegistration | Saving a registration successfully | Your Registration Request has been submitted to Fibrex successfully. Shortly you shall receive a confirmation email with the registration number.
Change Text | frmInternalRegistration | Saving a registration successfully | Your Registration Request has been submitted successfully. Registration Request #xxxx is created, pending approval.
Change Text | frmInternalRegistration/FrmRegistration | Saving a registration where Trade License Number already exists | Supplier with the same Trade License Number already exists.
Change Text | frmInternalRegistration/FrmRegistration | Saving a registration where Emirates ID already exists | Emirates ID number already exists.
Change Text | frmInternalRegistration/FrmRegistration | Saving a registration where the Company Name already exists | Supplier with the same supplier name already exists.
Implement | frmInternalRegistration/FrmRegistration | Saving a registration where the Official Email already exists. | Email address already exists; please input a different email.
Change Text | frmUpdateRegistration | Approving a supplier registration | Supplier # xxxxx is now available in the Supplier Master.
Change Text | frmUpdateRegistration | Adding an attachment | Attachment title has been added successfully but not committed; it would be committed when you commit the rest of the current transaction.
Change Text | login | Logining into a locked account. | Your account has been disabled.
Add Text | Add Attachment dialog | From Add Attachment, user clicks on OK without selecting a file. | No Attachments has been specified. Please select an attachment type and enter value into the corresponding field.
Change Text | frmAssignmentsDashboard > Search Supplier Profile Change Requests | loading the assignments page | Review and udpate the below Supplier Profile Change Requests

## Sheet2 (hidden)
Type | Priority | Status
Bug | Low | Open
Regression | Medium | Fix Available
Enhancement | High | Failed
New Development | Very High | Passed
Missing Function |  | Cannot Reproduce
Cancelled