## List
# | Page | Description | Reproduction Scenario | Referred Figures | Type | Priority | Tester | Developer | Status | ETA | Developer's Comments | Tester's Comments
1 | frmCreateNewPurchaseOrder | Remove asterisk from PO Number, Revision, Status and Status Date |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
2 | frmCreateNewPurchaseOrder | When selecting the organization, the ORGNAME should show on the form and not the code. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  | only did update purchase order, just to verify. If it is ok for you, I will implment on rest of the pages | It creation mode, it works fine. When opening an existing PO, it displays the code and not ORGNAME.
3 | frmCreateNewPurchaseOrder | Project is not being loaded according to the selected Organization. When selected, show the project code on the form. Disable Project until ORG is defined. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Keep select option in dialog box. Value should not be loaded when clicking ENTER. Issue with loading the projects when the organization name is updated. Make sure to refresh the projects when updating the organization.
4 | frmCreateNewPurchaseOrder | For all BUYER fields in the application, the dialog should only show the usernames who have security group = BUYER. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
5 | PO,POTEMPLATE | For all fields which have search icons associated to them, VALIDATE EVERY USER INPUT on both SAVE and field exist. If user enters any value which does not belong to the list, the system should highlight the field in red. Validation should be carried out on SAVE as well. Example: Invalid buyer name/Invalid Project/Invalid Organization |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | 1- Validation not carried out on SAVE. Server error shows. Test it for every single field which requires validation. 2- Contract ID not validated. 3- Same validation to be carried out for PO Tempalate on field change and save.
6 | PO table | Increase ORIGINALPONUM to 50 characters |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
7 | frmCreateNewPurchaseOrder | Vendor Date and Quotation Date are not mandatory. By default, ORDERDATE = curdate. The remaining dates should not be defaulted. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed |  |  | Vendor Date and Quotation Date should NOT be mandatory. Currently they are mandatory. Remove the asterisk. Order Date and Required Date are mandatory.
8 | frmCreateNewPurchaseOrder | Cannot navigate to next page from Select Supplier dialog box. System error returned. See figure 1. |  | Figure 1 | Bug | Very High | Hiba HALABI | Mohsan | Cannot Reproduce
9 | frmCreateNewPurchaseOrder | Vendor Name should be automatically populated when selecting Vendor ID. This field is disabled (not enabled for editing). When Vendor ID is updated, Vendor Name should be also updated. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
10 | frmCreateNewPurchaseOrder | PO Type dialog returns no results. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
11 | PO | 1- Revision comments is always disabled, and bounded to field po.REVCOMMENTS. (also remove Revision History defaulted value) 2- PO number is bounded to POREF and not PONUM. If null, insert Draft. 3- PO description length should be bounded to database field length. Make sure all remaining fields are bounded to the database data length. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Remove Description from being the defaulted value for PO Description. Remove organization defaulted value.
12 | POLINE | Auto-update of poline fields when updating LINEQTY, UNITPRICE, and LINECOST. |  |  | Bug | Low | Hiba HALABI | Mohsan | Passed |  |  | -If Quantity is updated, and Unit Cost is defined, update LINECOST. - If Quantity is updated, and Unit Cost is null or empty or zero, and LINECOST is defined-> update Unit Cost - If Unit Cost is updated, and Quantity is defined, update LINECOST. - If Unit Cost is updated, and Quantity is null or empty or zero, and LINE COST is defined -> update Quantity. - If LINECOST is updated, and Quantity is defined -> update Unit Cost. - If LINECOST is updated, and Quantity is null or empty or zero, and UNIT COST is defined -> update Quantity.
13 | POLINE | Add Supplier Reference to POLINE grid. (shrink the costcode column width) Title: Supplier Ref. Location: After Line Type Bind to db field: CATALOGCODE |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  | Update the SP as well, PO_ADDPOLIne PO_EditPOLIne PO_deletePoline
14 | POLINE | Delete, insert, and edit not working in certain cases. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  | There was a problem is updating the valus in session, it was fixed | - When deleting a row, and then inserting new row, POLINENUM can be equal to the value of the old row (since it was already deleted from table before new row was inserted). - A row is marked as UPDATED even though no update is done. Check the below query: select * from fsppo.dbo.A_POLINE where PONUM = '1019' and POREVISION = '0' and POLINEID = '46' Could be the page is not being refreshed, and it is still marked as update from the previous page save.
15 | Search PO | Project is null in results. Return Project Name and OrgName (not code). Enter space between first and last name for buyer. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
16 | PO | Add audit information to end of PO page, just like Registration page. |  |  | Bug | High | Hiba HALABI | Mohsan | Cannot Reproduce |  | I didn't find any difference , Last Modified date is same in PO, A_Po, when you create revision,it also update the last modified date. | Wrong audit. To reproduce, open PONUM = 1027, rev 0. The last modified date is incorrect, and does not comply with any value in the database. Seems you are discarding the revision when loading the dates.
17 | A_PO, A_POLINE | Audittimestamp should be datetime and not date only. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
18 | POLINE | clicking TAB after QTY, and attempting to type does not work. Issue with UOM. TAB does not work after QTY field. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
19 | POLINE | When a record cannot be inserted/edited in POLINE and procedure raises error, the error is not being reflected on application to the user, and the changes are discarded. | To reproduce, open a PO, and remove the QTY, UNITPRICE, and TOTALLINECOST from a given POLINE where LINETYPE = ITEM. Click save. The record is not saved, changes are discarded without returning to the user. |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Server error.
20 | Attachments | Error when trying to add a valid attachment |  | Figure 2 | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Distorted dialog box. Take long time to attach and result in error.
21 | POLINE | Do not auto update SUBCOST and TOTALCOST in POLINE header. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  | updated issue fixed | Do not auto-update those two fields! Show the fields on POLINE but do not undergo ANY CALCULATION.
22 | Revise PO | Revise PO is not working. It should start by calling the procedure PO_GETNEXPOREV. If it returned an error, then the dialogbox should NOT show, and the same error should be returned to the user. Otherwise, display the dialog box showing in Revision, the returned revision number from procedure output. | To reproduce, go to Search PO, open PO 1006. Click Revise PO, the dialog box shows with wrong information. On the contrary, if you call the procedure, it returns an error! declare @nextrev smallint exec fsppo.dbo.PO_GetNextPORev '1006', '0', @OUTPUTNEXTREV = @nextrev OUTPUT print (@nextrev) |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  | I updated SP, Change in RaiseError, after that, I update in the code
23 | Change Status | Clicking on Change Status returns an error. | To reproduce, open registration #1006. Click on Change Status. It will return an error. |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
24 | Print PO | print PO should open in a NEW TAB. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
25 | View Revision History | Clicking on View Revision History returns an error. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
26 | PO | Opening any PO returns an error. See figure 3. |  | Figure 3 | Bug | Very High | Hiba HALABI | Mohsan | Passed
27 | New Contract | Upon creating a new contract, clicking on Organization and attempting to select a given value does not work |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
28 | New Contract | Upon creating a new contract and filling into all values, clicking save returns no action! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed | Figure 15 |  | Check Figure 15. Error when saving.
29 | Load PO Template | Dialog box should show the below columns in order: - Template Name - Organization (Name) - project Name - Vendor Name - Created By No filter should be available on 'select' option. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Filter should be available on first column (i.e. Select) - Vendor Name search filter is not working.
30 | Search PO Templates | Filters & grid output. Template Name Template Description Organization (filter) Project(filter) Vendor(filter) Created by (filter) Created after (calender) in the output, the link should be on Template ID (first column) which is the same behavior for Registration, Supplier, and PO. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | - First column should be template ID. - By filter, I mean add them as filter in the search criteria and not in the grid. Behavior should be same like all other search pages.
31 | Po Templates | Vendor ID/Vendor Name is not mandatory. Mandatory information are: Organization & Buyer |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Project is mandatory. Type is not mandatory.
32 | PO Templates | Vendor ID/Vendor Name should be disabled and attain same behavior like PO. Unable to select a Vendor ID from dialog box. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | Create Contract is not working. Clicking on SAVE does not result in any update on the databae, and does not return any error to the user.
33 | PO Templates | Add audit information to the end of the PO Template Page. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  |  | Create Contract is not working. Clicking on SAVE does not result in any update on the databae, and does not return any error to the user.
34 | PO Templates | Add Template ID and Template Owner in the Templates Information section. Rename Templates Information to Template Header. Template Owner = Logged in user. The Template ID and Template owner will show upon saving, and when editing an existing template. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  |  | Create Contract is not working. Clicking on SAVE does not result in any update on the databae, and does not return any error to the user.
35 | PO/PoTemplates | Disable vendor ID from PO/Edit PO/PO Templates/Edit Po Template pages |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
36 | Dialog boxes with filters | % should be accepted by all filters in dialog boxes. See Figure |  | Figure 4 | Enhancement | High | Hiba HALABI | Mohsan | Passed |  | I give Row filter option on every grid Like, Contain, doesn't contain, equal, less then, greater then. | Filters not working
37 |  | Change datatype of ORDERTYPE, REQUIREDATE, VENDORDATE, and QUOTATIONDATE to DATE and not DATETIME in all relevant tables and procedures. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
38 | PO | - When a purchase order is successfully created, return a confirmation message to be referred to from SS_MESSAGES. - When PO change Status is successfully applied, return confirmation message to user: Status successfully updated. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
39 | Errors | When an error is shown for any reason, if user removes the error, and apply any operation on the page, the old error is reshowing. |  |  | Bug | High | Hiba HALABI | Mohsan | Cannot Reproduce |  |  | [2017-07-16] Open PO F-3-ALD001-PUR-2-2017, Rev 1. Error shows. Still the case when calling Revise PO for example. Old errors still show.
40 | PO print | If only one supplier is defined, the grid should show only one line in Supplier Details. If VENDORATTN2NAME is null, show one row. Else, show 2 rows. |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Open
41 | PO, Contract | Upon saving a PO (creation or edit mode), check whether the underlying Vendor is blacklisted. If supplier status blacklisted, return warning: The selected vendor %vendorname is blacklisted. Encode in SS_Messages |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available |  |  | [2017-07-19] Wrong paramter being passed to the error message. Instead of passing the selected blacklisted vendor, you are passing the field value. [2017-07-13] Behavior not working for Contract. Also, update the design. [2017-11-07] (1) Do not load the values unless the user confirms. (2) The dialog box design is not coherent with the rest of the application. Redesign required. Change the behavior: On VENDORID field change, if selected supplier is blacklisted, show dialog box with warning message, and two buttons: Confirm and Discard. Clicking on Confirm loads the suppliers details. Clicking discard does not load the user selection, and field maintains the previously selected value.
42 | PO | The below fields should not be mandatory (creation/update mode): Supplier Contact 1 Fax, Supplier Contact 1 Email, Supplier Contact 1 Phone |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed |  |  | Asterisks missing on mandatory fields.
43 | PO, POTEMPLATE | When a field is highlighted in red, once the user type into it, the highlight should be removed. | To reproduce, create a PO without defining the Supplier Contact Information. Click SAVE. Mandatory fields are highlighted in red. Once defined, the border should be removed, but it still persists. |  | Bug | Medium | Hiba HALABI | Mohsan | Passed |  |  | - Not done for PO Project. - Not done for all Organization, Project, and Type in PO Template.
44 | Pending PO Assignments | - Increase PO Ref. Increase Vendor. Decrease Project. - Order by descending order of Creation Date. - In underlying query, add condition: where buyer = loggedin user. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
45 | Search PO | -Organization filter should show name and not code. -Project filter should show name and not code. - In results, PO REF should be left-aligned, not center-aligned. - None of the filters are working. - Add checkbox View Revisions History, as specified in the specs for which you need to search also from POARCHIVE and POLINEARCHIVE. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | - Buyer filter is not working - Search Revisions History flag is not working - Clicking on ENTER returns error. - Creation Date not working. To reproduce, search on POREF F-3-ALD001-PUR-2-2017, Rev 1, and put in Creation DATE 05-Jul-2017. It returns no results. - When clicking on the Search button do not redirect the user to LINES tab. maintain the selected tab. - Clicking on Clear button does not respond. It should clear all search criteria, and reload data, including Search Revisions History checkbox (should be deselected).
46 | Refresh PO | Refreshing the page should reload the form, and not resubmit it. - When a change is detected, the system should return warning message. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  | Fixed on All Pages, PO, EDIT PO, Create Templates, Edit Templates | [2017-07-11] 1- Not done on PO Description, Supplier Contact 1 Email, Supplier Contact 2 Email 2- Not done on Attachments. 3- Not done on POLINE Less and Additional Charges (4 fields). (this is i already done, i remove it for the testing purpose because i was apply mask on it.) 4- Not done on POLINE Line Type 5- Not done if a POLINE is deleted. Refreshing is not prompting the user to confirm page refresh or discard changes, when one or more fields are changed.
47 | PO | Buyer field value should show username and not first name. Validation should also be carried on username and not first name, in creation and edit modes. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
48 | POLINE | LINEQTY, LINECOST, and UNITCOST are rounding up to integers. Should be defined as numbers with 2 decimal points. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
49 | Serve Error | The application SHOULD NOT RETURN SERVER ERROR UNDER ANY CIRCUMSTANCE! Show the error on the front-end. This is a critical issue. REVIEW THE ENTIRE CODE! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
50 | POLINE | Error when trying to update PO grid and saving. Reference attached figure. |  | Figure 5 | Bug | Very High | Hiba HALABI | Mohsan | Passed
51 | Contact | Contracts relationship is NOT WORKING! When adding a contract and clicking on save, nothing happens! No error is returned to user, and no action is undertaken. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Cancelled
52 | POLINE | Start with POLINENUM = 1 and not 0. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
53 | Attachments | Update on PO Attachments is not working. The record is being discarded. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
54 | PO | When PO Status is approved, the second tab featuring POLINE grid and additional charges should all be disabled. Keep attachmets open. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | - Attachments should be kept open. - POLINE grid lines should be diabled. Delete option should be disabled as well.
55 | PO | PO Revision comments is not reflecting PO.REVCOMMENTS field value. | To reproduce, open PO F-3-ALD001-PUR-1-2017, Rev 1. Revision comments is empty, although REVCOMMENTS in defined in PO table for the underlying PONUM and REVISION. | Figure 6 | Bug | High | Hiba HALABI | Mohsan | Passed
56 | PO | When changing status of PO rev > 0 to approved, application is showing successful status update, when nothing is taking place. | To reproduce, go to PONUM = 1019, Rev 1. Change Status to approved. Click Submit. It shows Status Updated successfully, but the status is still PNDREV. |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
57 | Print PO | POLINE grid not showing | To reproduce, go to PONUM = 1019, rev 1 and print PO. Grid is not showing, |  | Regression | Very High | Hiba HALABI | Mohsan | Passed
58 | PO | When entering valid organization directly without prompt, then selecting from prompt project, then entering valid type without promot, then entering any values for remaining fields -> selecting a vendor does not populate its details in the form. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
59 | Search PO | - Do not carry validations on Search PO search fields: Organization, Project, Type, and Buyer. % sign should be accepted, and running successfully. - Clicking on Enter should be equivelant to clicking on earch button. Currently error shown in Figure 7 is returned. There is no minimal selection on criteria. |  | Figure 7 | Bug | High | Hiba HALABI | Mohsan | Passed
60 | Search PO | - None of the fields in the tabs are working! POLINE, DATES, and Reference documents. - Return error if value in dates fields is not a DATE. Error is already encoded in SS_MESSAGES |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  | It showing No data to display | [2017-07-18] Application crashing on Required Date and Creation Date fields. Currently, if date is not accepted, the database error is being return. Return the error encoded in SS_MESSAGES which also reflects the field name
61 | Search PO | Search Revisions History checkbox does not work |  |  | BUg | High | Hiba HALABI | Mohsan | Passed
62 | POLINE | Description and TOTALCOST are mandatory fields. Validate on save. Description cannot be empty string or null (after trim). Totalcost should not be zero or empty string or null. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Should be done on application level. Validate on Save. Write a method to check for mandatory fields to be called from SAVE, or alternatively you may be requested to call it on Add Row.
63 | POLINE | Validate UNITCOST, QTY, LINECOST, Less Amount, Additional Amount on fieldchange/fieldexist. It should be decimal values ONLY. i.e. attempt to convert the value to number (10,2). If it resulted in error, return error to the user immediately. Save validation should be carried on save. Should reference one record in SS_MESSAGES with field name as parameter. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Not done on Less Amount and Additional Amount.
64 | Change PO Status | Cannot approve a PO, if there isnt at least one line in the POLINE grid. |  |  | Enhancement | Medium | Hiba HALABI | Hiba HALABI | Passed |  | Handle with Code, I already add Error masgs in SS_Message
65 | Search PO | Getting error show in Figure when searching for PO. |  | Figure 8 | Bug | High | Hiba HALABI | Mohsan | Passed |  | This error is showing because project will be loaded on the base of Organization. | Showing when clicking ENTER.
66 | PO | All PO References fields (4 fields) should not be mandatory. Plus remove asterisk. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
67 | POLINE | Adding a new row, which results in an error, then deleting it, and attempting to re-insert a new row is not possible -> no action takes place. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
68 | POLINE | When bypassing the description (without entering a value), error shown in figure 9 is being displayed. |  | Figure 9 | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | Caused regression. Anomaly 114
69 | POLINE | For the PO_deletePOLINE, you are not passing DATETIME to procedure. Only date is being passed by. |  | Figure 10 | Bug | High | Hiba HALABI | Mohsan | Passed
70 | POLINE | When user on a specific tab, and did any action resulting in an error, the error should be shown on the same tab without redirecting the user to PO tab. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
71 | Report | Complete PO DISTRIBUTION BY BUYER report. Linked to procedure po_report_podistbybuyer. Show input parameters and output. Make sure all filters are working properly. |  |  | New Development | High | Hiba HALABI | Mohsan | Fix Available
72 | Report | Complete PROJECT SPEND BY COSTCODE report. Linked to procedure po_report_projectspendbycostcode. Show input parameters and output. Make sure all filters are working properly. |  |  | New Development | High | Hiba HALABI | Mohsan | Fix Available
73 | Report | Complete SPEND BY TOP SUPPLIERS report. Linked to procedure po_report_spendbytopsuppliers. Show input parameters and output. Make sure all filters are working properly. |  |  | New Development | High | Hiba HALABI | Mohsan | Fix Available
74 | Report | Complete SUPPLIER PURCAHSE SUMMARY report. Linked to procedure po_report_supplierpurchasesummary. Show input parameters and output. Make sure all filters are working properly. |  |  | New Development | High | Hiba HALABI | Mohsan | Fix Available |  |  | [2017-07-20] Errors should show on the application, and not the report printout! - Rename Company ID to Vendor ID. - In the report, add mask to quantity, UNITCOST, and LINECOST
75 | Report | Complete COMPARE PRICE BY ITEM report. Linked to procedure po_report_comparepricesbyitem. Show input parameters and output. Make sure all filters are working properly. |  |  | New Development | High | Hiba HALABI | Mohsan | Fix Available |  | -Item description is not being returned. - Fix grid design to match rest of application | - Add Org Name instead of Org Code. Name as as Organization. - Remove Vendor ID. - Show first 50 characters only from Supplier Name. Can be expanded. Shrink Supplier Column. - Move Buyer and Order Date to the end of the grid results. - When clicking on any header in the grid for sorting, the results disappear. - New line not showing for description (In report it was fixed) - Output grid in the report should be the same as that returned by procedure. Plus, buyer name is not showing. - Change layout to landscape. - SHow PO Ref instead of PONUM - Show Order Date as Date not Datetime - Show POREF and not PONUM - Add Mask on Quantity, Unit Cost, and Line Cost in both output grid and printed report. - Clicking Enter returns error. It should be equivelant to running the report.
76 | Dashboard | Complete dashboard: Approved Purchase Orders Contracts Purchase Orders Pending Review PO Status Distribution PO Distribution by Organization PO Distribution by Project PO Distribution by Buyer Contracts Distribution by Type |  |  | New Development | High | Hiba HALABI | Mohsan | Passed | z | Regarding screenshot, project code is same and project name is different, I already explain you | - Rename Pending Revision PO to Purchase Orders Pending Revision. - For PO Status Distribution: Change colors (ask hiba) - For PO Distribution by Organization, it should consider only PO with Status APRV. Underlying query: select ORGCODE, COUNT(*) from FSPPO.dbo.PO where status = 'APRV' group by ORGCODE Rename title to Approved PO Distribution by Organization. - PO Distribution by Status: Failed. See related figure. Also, enhance it to include only APRV POs ONLY. - PO Distribution by Buyer: also for Approved POs only.
77 | POLINE | The below fields should be bounded as mandatory if one of them is defined: - Less Amount & Description - Additional Amount & Description |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
78 | POREF | Align POREF to the LEFT not center in all search pages. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
79 | PO | PAYMENT TERMS is not bounded to length in database. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
80 | POTEMPLATE | Do not pass empty string to procedure input paramteres, when NULL is expected. Some field values are null and others are empty string. | To reproduce: run the query: select * from fsppo.dbo.POTEMPLATE where POTEMPLATEID = '15' |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
81 | CONTRACT | In Add Contract dialog box, show the below fields in order: - Contract Type - Original Contract Number - Organization (ORGNAME) - Project (PROJECTNAME) - Vendor (VendorNAME) - Creation DATE Add filters for all. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  | Add filters with options just in like in PO. > Contracts dialog box. | Show the Original Contract Number. Rename Contract Num to Contract ID. Should be done in both Contracts and PO pages.
82 | REPORTS | Validate input on all reports. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
83 | PO | 1- In Contracts dialog box, show Organization Name after Contract Type. (Done) 2- Filters in following order: Contract Num, Contract Type, Organization, Project, Vendor Name, Start Date (Done) 3- Show Start Date as DATE not DATETIME. (Done) 4- Add Calender filter to StartDate, where underlying query should be >= specified date |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed |  | Checking the 4th point, checking the greater then condition
84 | PO, POLINE, CONTRACT | Add mask for the below fields: PO TOTAL COST, PO SUBTOTAL COST, PO LESS AMOUNT, PO ADDCHARGES AMOUNT, POLINE QTY, POLINE UNITCOST, POLINE COST, CONTRACT AMOUNT |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed |  |  | -Quantity should have precision (16,4). Currently the precision is 2. Upon saving, the additional decimals are discarded. -Wrong mask for Contract Total Amount -Remove default values. Becomes difficult to edit the value. Should be done for all fields.
85 | PO, POLINE, CONTRACT | In all tables with reference to the below fields, change data type from numeric(10,2) to numeric(16,4) DISCOUNT, ADDCHARGES, SUBTOTALCOST, TOTALCOST, LINECOST, UNITCOST, CONTRACTAMOUNT |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed |  |  | Not imlemented for audit tables.
86 | Session expiry timer | Add session expiry timer set as 120 seconds to be preempted to user once started. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Postponed |  | I warn the user 2 min before, so he/she can save data. | This solution is not acceptable. Should show dialog box with countdown in seconds. Postponed after all anomalies are completed.
87 | Tasks, Search PO | Error on Tasks page. See figure |  | Figure 11 | Bug | High | Hiba HALABI | Mohsan | Passed
88 | PO | When saving PO, procedures to update PO and POLINES should NOT be called unless a change is detected. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
89 | POLINE | When inserting a POLINE, then deleting an existing POLINE, the error shown in Figure 12 is being returned. | To reproduce, go to PONUM 1027, Rev 0, insert new line, delete line 2. Save. | Figure 12 | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | Cause regression. All values in the newly inserted rows are being nullified.
90 | CONTRACT | Original contract Number in Contracts and Original PO Number in PO should not accept spaces. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed |  |  | Original Contract Number does not accept any character. It should only discard spaces.
91 | Contract | Contract dialog should be same as that in PO.RelatedContractID |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
92 | Contract | Related contracts grid should show Last Updated Date as DATETIME. See figure 13. |  | Figure 13 | Bug | Low | Hiba HALABI | Mohsan | Passed
93 | Contract | In the grid of related contracts, show Contract ID as first column, and Original contract number should reflect the correct field in the database. Currently it reflects ContractNum, which is not correct. |  | Figure 14 | Bug | High | Hiba HALABI | Mohsan | Passed
94 | Contract | When clicking on View all Contracts menu, the menu is changing to that of PO. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
95 | Contract | In Edit Contract, show Contract Header, which is Contract ID and Contract Status. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
96 | Contract | Add Audit information to end of Contract page, just like PO and Registration. |  | Figure 19 | Bug | Medium | Hiba HALABI | Mohsan | Passed |  |  | - Should be reading from audit table of A_Contract and A_ContractRef. For example, when deleting a contract and saving, the audit timestamp is not being updated at the end of the page. Wrong audit information. See Contract 22 / figure 19. The Last Modified By and Date are wrong.
97 | Contract | Add Quotation Ref and Quotation Date fields in Contracts general information, while binding the two fields to QNUM and QDATE respectively. Update the design as shown in the figure. |  | Figure 16 | Enhancement | High | Hiba HALABI | Mohsan | Passed |  |  | - Quotation Ref data field length is not bounded to database. - If Quotation Date, Start End, End Date are not in the correct format, return the message encoded in SS_Messages reflecting the concerned field name.
98 | Contract | LASTMODIFIEDBY and LASTMODIFICATIONDATE showing as NULL in CONTRACT table. | To reproduce, run the below query: select * from fsppo.dbo.CONTRACT where CONTRACTNUM = '10' |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Cannot test due to error in save.
99 | Contract | The grid of associated contracts does not load data correctly from CONTRACTREF and CONTRACT tables. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
100 | PO | When successfully creating a new revision, load the new revision instead of maintaining the old revision page. Confirmation message should show on the new page. | To reproduce, open any PONUM and create a new revision on revision 0. Once successful, the old page is still being loaded with a confirmation message that the new revision has been successfully created. Enhance the behavior so that the page loads the same PONUM and newly created revision. Make sure the confirmation message shows on this page instead. |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
101 | PO | If POREF is not null for the underlying PO, ORG, PROJ, and VENDOR ID should be disabled. Only if POREF is null, those fields are enabled. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
102 | PO | When changing the status of PO rev 1, the memo is also showing in REVCOMMENTS of same PONUM, rev 0 |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
103 | PO | Contract ID should not be mandatory. No validation to carry on the field if NULL. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
104 | PO | LASTMODIFIEDDATE in PO table reflects DATE only and not DATETIME. | To reproduce, run the below query: select * from fsppo.dbo.PO where PONUM = '1028' and POREVISION = '0' |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
105 | PO, A_PO | STATUSDATE showing as DATE instead of DATETIME in both PO and A_PO | To reproduce, run the below query: select * from fsppo.dbo.PO where PONUM = '1028' and POREVISION = '0' select * from fsppo.dbo.A_PO where PONUM = '1028' and POREVISION = '0' |  | Bug | High | Hiba HALABI | Mohsan | Passed
106 | Compare prices report | Error when running Compare Prices report, when the underlying query is returning results successfully. |  | Figure 17 | Bug | Very High | Hiba HALABI | Mohsan | Passed
107 | All REPORTS | IN all reports, when no values is specified, pass NULL and not empty string in the procedure. |  |  | BUg | Low | Hiba HALABI | Mohsan | Fix Available
108 | PO | In PO, creation and udpate mode, show ORIGINALCONTRACTNUM in Contract # field. Store ContractID in the database (key). |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
109 | Contract | - Increase size of VENDORNAME. Bind Total Amount to database allowable length. - Grid should show: Contract ID and Original Contract Num - Grid should show Last Modified By as DATETIME and not DATE. - Vendor Name should reflect same length as SUPPLIER.SUPPLIERNAME - Audit Information does not show Last Modified By |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
110 | POLINE | -Increase the precision for all fields. - When updating the Total price, the UNIT price should be only updated, without re-updating Total price. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  | In this case, we have implment the floor or ceiling funtion
111 | POLINE | When udpating supplier reference CATALOGCODE, the system is detecting an update, and a new record is being inserted in A_POLINE, but the actual value is not being updated. i.e. updated on CATALOGCODE are discarded. | select * from fsppo.dbo.A_POLINE where PONUM = '1031' and POREVISION = '0' |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
112 | POLINE | Updates on LINETYPE and COSTCODE are discraded. Same behavior witenssed for anonaly 111 |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
113 | POLINE | Adding a new drops the values for the first 3 columns | To reproduce, go to PONUM = 1031, rev 0, and add a new row to the existing grid with 2 rows. Once the first 4 fields are defined, the are nullified. |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
114 | PO | Add PONUM as label as below. - Shows only if underlying user has permission FSP_ADMIN - Font: Black, italic - Position: see figure |  | Figure 18 | Enhancement | High | Hiba HALABI | Mohsan | Passed
115 | CONTRACT | When ANY action is undertaken on any field or on the related contracts, attempting to refresh the page should return a warning |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  |  | - Not done for Subject and Mobile fields. - Not done after user inserts a new contract relationship. Done for delete only.
116 | CONTRACT | When updating a contract, if user changes any field, then clicks on Add Contract button, the warning 'Changes will be discarded' shows! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
117 | CONTRACT | Error when updating contract. See figure 20. Possibly related to Total Amount. |  | Figure 20 | Bug | Very High | Hiba HALABI | Mohsan | Passed
118 | Contract | Cannot update Total Amount! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  | Resolved the update problem. | Update is not working properly. Issue with mask.
119 | Contract | When adding a new Contract, return error if Original Contract Number already exists in database. Update ADD and Edit contract procedures. |  |  | Enhancement | Medium | Hiba HALABI | Hiba HALABI | Passed |  |  | Assigned to hiba to update procedures.
120 | PO | When adding a new PO, return error if Original PO Number already exists in database for the same division and project. Update ADD and Edit PO procedures. |  |  | Enhancement | Medium | Hiba HALABI | Hiba HALABI | Passed |  |  | Assigned to hiba to update procedures.
121 | POTEMPLATE | Return error if user selected a blacklisted supplier from dialog. Templates on blacklisted suppliers are not permitted. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
122 | POTEMPLATE | Cannot update Vendor Address and Ship to Address. User input value is not accepted. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
123 | PO | Cannot update PO Status to Cancelled. Error as shown in figure 21 |  | Figure 21 | Bug | Very High | Hiba HALABI | Mohsan | Passed
124 | Search PO | For all 4 fields in DATES tab, if From date is greater than To Date, return error from SS_MESSAGES, ID = 1034 |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Passed |  |  | Reference SS_Message ID = 1034
125 | PO | Edit and Delete attachments not working. |  |  | Regression | Very High | Hiba HALABI | Mohsan | Passed
126 | PO | When PO Status = Revised, disable PO and POLINES grids, just like approved. Editing a revised PO is not permitted. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
127 | PO Change Status | Procedure returns an error if there is not at least one PO LINE defined for the underlying PO revision. However, from the application, when clicking on Change PO Status, clicking on Submit returns an error on the first time. Clicking Close changes the status to approved. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed |  | Need to check the SP PO_ChangeStatus, SP give an error, after error it commit the transaction | Change the behavior clarified in anomaly 137
128 | Seach PO | Error when searching on PO because the fields are not bounded to their datatypes on lengths in the database. See figure. |  | Figure 23 | Bug | Medium | Hiba HALABI | Mohsan | Passed |  |  | Still getting the error. Make Revision accept only numbers.
129 | Search PO | If the 4 dates in the DATES tab of Search PO are not in the correct format, return the message encoded in SS_Messages reflecting the concerned field name. |  |  | Bug | Low | Hiba HALABI | Mohsan | Passed |  |  | Done for the first 2 fields only.
130 | Contract | In create and edit Contract, if Contract Start Date > Contract End Date, return error encoded in SS_Messages |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Passed
131 | Contract | - Error upon updating Contract information. Concerned fields: Mobile and Email - Update on Payment terms is discarded. |  | Figure 25 | Bug | Very High | Hiba HALABI | Mohsan | Passed
132 | PO | Incorrect audit information reflected for PO page. To reproduce, go to any PO revision, update Order date only, and save. The audit information is not updated. Make sure you take the maximum timestamp from the below 3 tables: - A_PO for same PO num and revision A_POLINE for same PO num and revision Discard attachments. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
133 | POLINE | When typing the description, the first characters are being discarded. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Failed |  |  | Solve it by making the response faster. Behavior is not acceptable, and a solution should be provided.
134 | PO/POLINE | When PO Status is cancelled/approved/revised, the PO tab, and second tab featuring POLINE grid and additional charges should all be disabled. Keep attachmets open. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
135 | Contract | For Add new Contract dialog box, fix the distorted design, and add Original Contract Num as second column. |  | Figure 26 | Bug | Medium | Hiba HALABI | Mohsan | Passed
136 | PO | Error when updating POLINE. Arithmetic overflow. Check datatypes in procedures. |  | Figure 27 | Bug | Very High | Hiba HALABI | Mohsan | Passed
137 | PO | If system detected any change on PO page, then clicking on Change Status or Revise PO, should return to the user "System detected a change on the PO. Click Cancel to return to PO page and save your changes. Click continue to discard your changes. " If user clicks Continue, refresh the page and load the dialog box. If user clicks Cancel, go back to the page. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Open |  |  | Clicking OK should reload the page (i.e. user chose to discard the changes)
138 | POLINE | POLINE Quantity mask is not working |  |  | Bug | Very High | Hiba HALABI | Mohsan | Passed
139 | POLINE | Under POLINE > Charges, when user clicks on TAB from Less field, it should navigate to Less Amount. Apply the same behavior for the four fields. |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Passed
140 | Print PO | - Rename Division to Organization. Reflect OrgName and not Project Name. Put on top. - Rename Agent to Buyer. Should show full name and not username. - New Line (\n) is not reflected in POLINE Item description (high priority bug) - Mask is not reflected on Quantity field in PO Printout |  | Figure 34 | Bug | Very High | Hiba HALABI | Mohsan | Fix Available |  |  | [2017-07-20] Quantity is not showing on report. - Less and Total Amount not showing. - New Line is not displayed consistently. Go to PO: 1040, Rev 0. Print PO and compare with POLINE grid. Printing result in server error. Check PO 1035.
141 | PO | - Contact Person 2 Position Under Delivery Information is not bounded to its corresponding field in database. - Less Description and Additional Charges Amount are not bounded to their length in database. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
142 | PO | When saving Vendor Date = date present in Required Date. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
143 | print PO | Amend Additional Charges and Less Charges Description and Amounts fields to the end of the report. - Subtotal should read from database. - Show Grand Total Amount: Read from database. |  |  | Enhancement | Very High | Hiba HALABI | Mohsan | Fix Available |  | If I hide the additional charges and discount, it show the spaces on that particular area | - Check seperately if Less Amount is 0 or null, and if Additional Charges amount is 0 or null. Accordingly, chose whether or not to display the line in printout.
144 | Load PO Template | When loading PO Template, show only templates where Template Owner = logged in user. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available |  |  | To be done on dialog box when choosing to load a template as well.
145 | Load PO Template | When no project is found, return NULL and no Project Not found. See referenced figure. |  | Figure 28 | Bug | Medium | Hiba HALABI | Mohsan | Cancelled |  | This massage is coming because project was not implemented with IMS, Now Project is not integrated with IMS.
146 | All Dialog boxes! | For any dialog box in the application, when filtering on specific filters, then reloading the dialog boxes again, show the previous user filtering options. Reset everytime the dialog boxes are called. Make sure it is done for every dialog box in every page, including Load PO Template. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
147 | POLINE | Open any PO Revision, update PO description, and click TAB, the changes are immediately discarded. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available |  | point 133, 147, I try to improve the performace as much as I can do..
148 | Change PO Status | Change status from PNDREV -> APRV returns an error (subquery returned more than one value). Error is bypassed, and closing the dialog approves the PO, when it should not. |  | Figure 29 | Bug | High | Hiba HALABI | Hiba HALABI | Passed
149 | PO | Update on PO Description field is being discarded from POLINE and ATTACHMENTS tabs. |  |  | Bug | Medium | Hiba HALABI | Mohsan
146 | Contract | Cannot add attachment to a Contract. The records are not being inserted in database tables, and no error is being returned!!! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
147 | Contract | The error returned by procedure po_addcontractref are showing in green, and not red! |  | Figure 30 | Bug | Medium | Hiba HALABI | Mohsan | Passed
148 | Search PO Templates | 1- Revise filters as follows: Template Name, Template descirption, Organization, Project, Vendor, Created By. 2- Bind all fields to their corresponding data type and lengths in the database. Also, ID should accept only number. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
149 | PO Templates | PO TYPE validation is not carried on SAVE. To reproduce, enter any value for PO Type, system returns an error. Ignore the error, and click save, the value is nullified and template is saved. - Same behavior witnessed for Project field. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Passed
150 | PO Templates | The below fields are NOT bounded to their lengths in the database. - Supplier Contact 1 Position - Supplier Contact 1 Email - Supplier Contact 2 Position - Supplier Contact 2 Email - Payment terms |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
151 | PO Templates | When a Template is updated successfully, no confirmation message is being returned. Return message 1070 from SS_MESSAGES |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
152 | POLINE | In POLINE grid Quantity, Unit Cost, Total Cost, Less Amount, and Additional Charges Amount, when user clicks tab, and cursor gets transferred to the field, select the field value to ease data modification. Otherwise, user will have to erase the existing content and type; prone to error. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Open
153 | POLINE | Mask not showing for Subtotal and Total cost amounts. See referenced figure. |  | Figure 31 | Bug | High | Hiba HALABI | Mohsan | Passed
154 | Search PO | Cannot select a project. See referenced figure. Rename Company to Vendor |  | Figure 32 | Bug | High | Hiba HALABI | Mohsan | Fix Available
155 | View Revision History | REVCOMMENTS is reading input from STATUS comments. Wrong. Should read from REVCOMMENTS in PO table for underlying PONUM and POREVISION. |  | Figure 33 | Bug | High | Hiba HALABI | Mohsan | Cancelled
156 | All reports | For all 5 reports, any amount should be displayed with mask. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
157 | All reports | Apply the below validations on START DATE and END DATE in all reports: - Start date should be less than or equal to End Date. Reference error 1034 in SS_MESSAGES. - Start date/End Date should be in correct format. Reference error 1033 in SS_MESSAGES. |  |  | Bug | Medium | Hiba HALABI | Mohsan | Fix Available
158 | POLINE | When I tried adding 10 lines, and attempted to delete the last line, the delete button was not responding! |  |  | BUg | Very High | Hiba HALABI | Mohsan | Fix Available

## Figures
Figure 1
Figure 2
Figure 3
Figure 4
Figure 5
Figure 6
Figure 7
Figure 8
Figure 9
Figure 10
Figure 11
Figure 12
Figure 13
Figure 14
Figure 15
Figure 16
Figure 17
Figure 18
Figure 19
Figure 20
Figure 21
Figure 22
Figure 23
Figure 24
Figure 25
Figure 26
Figure 27
Figure 28
Figure 29
Figure 30
Figure 31
Figure 32
Figure 33
Figure 34

## POLINE
Action 1 | Action 2 | Status
NULL | Insert | not working for line 2 and beyond
Insert | Edit | Not working
NULL | Edit | working
NULL | Delete | working

## Sheet2 (hidden)
Type | Priority | Status
Bug | Low | Open
Regression | Medium | Fix Available
Enhancement | High | Failed
New Development | Very High | Passed
Missing Function |  | Cannot Reproduce
Cancelled
Postponed