## List
# | Page | Description | Reproduction Scenario | Referred Figures | Type | Priority | Tester | Developer | Status | ETA | Developer's Comments | Tester's Comments
1 | frmCreateNewPurchaseOrder | Remove asterisk from PO Number, Revision, Status and Status Date |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
2 | frmCreateNewPurchaseOrder | When selecting the organization, the ORGNAME should show on the form and not the code. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  | only did update purchase order, just to verify. If it is ok for you, I will implment on rest of the pages | It creation mode, it works fine. When opening an existing PO, it displays the code and not ORGNAME.
3 | frmCreateNewPurchaseOrder | Project is not being loaded according to the selected Organization. When selected, show the project code on the form. Disable Project until ORG is defined. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Keep select option in dialog box. Value should not be loaded when clicking ENTER. Issue with loading the projects when the organization name is updated. Make sure to refresh the projects when updating the organization.
4 | frmCreateNewPurchaseOrder | For all BUYER fields in the application, the dialog should only show the usernames who have security group = BUYER. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Passed
5 | frmCreateNewPurchaseOrder | For all fields which have search icons associated to them, VALIDATE EVERY USER INPUT on both SAVE and field exist. If user enters any value which does not belong to the list, the system should highlight the field in red. Validation should be carried out on SAVE as well. Example: Invalid buyer name/Invalid Project/Invalid Organization |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available |  | on User Input Type, it validate only first 10 records. I am checking this. Will update you soon | Validation not carried for Contract.
6 | PO table | Increase ORIGINALPONUM to 50 characters |  |  | Enhancement | High | Hiba HALABI | Mohsan | Passed
7 | frmCreateNewPurchaseOrder | Vendor Date and Quotation Date are not mandatory. By default, ORDERDATE = curdate. The remaining dates should not be defaulted. |  |  | Enhancement | High | Hiba HALABI | Mohsan | Fix Available |  |  | Vendor Date and Quotation Date should NOT be mandatory. Currently they are mandatory. Remove the asterisk. Order Date and Required Date are mandatory.
8 | frmCreateNewPurchaseOrder | Cannot navigate to next page from Select Supplier dialog box. System error returned. See figure 1. |  | Figure 1 | Bug | Very High | Hiba HALABI | Mohsan | Cannot Reproduce
9 | frmCreateNewPurchaseOrder | Vendor Name should be automatically populated when selecting Vendor ID. This field is disabled (not enabled for editing). When Vendor ID is updated, Vendor Name should be also updated. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
10 | frmCreateNewPurchaseOrder | PO Type dialog returns no results. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed
11 | PO | 1- Revision comments is always disabled, and bounded to field po.REVCOMMENTS. (also remove Revision History defaulted value) 2- PO number is bounded to POREF and not PONUM. If null, insert Draft. 3- PO description length should be bounded to database field length. Make sure all remaining fields are bounded to the database data length. |  |  | Bug | High | Hiba HALABI | Mohsan | Passed |  |  | Remove Description from being the defaulted value for PO Description. Remove organization defaulted value.
12 | POLINE | Auto-update of poline fields when updating LINEQTY, UNITPRICE, and LINECOST. |  |  | Bug | Low | Hiba HALABI | Mohsan | Fix Available
13 | POLINE | Add Supplier Reference to POLINE grid. (shrink the costcode column width) Title: Supplier Ref. Location: After Line Type Bind to db field: CATALOGCODE |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available |  | Update the SP as well, PO_ADDPOLIne PO_EditPOLIne PO_deletePoline
14 | POLINE | Delete, insert, and edit not working in certain cases. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
15 | Search PO | Project is null in results. Return Project Name and OrgName (not code). Enter space between first and last name for buyer. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
16 | PO | Add audit information to end of PO page, just like Registration page. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available |  | In PO Table, If vender name is less then 50 it, expect this, if vender name legnth is more then 50, it give me an error, string and binary data. Even in table and SP we define is vendername is 100
17 | A_PO, A_POLINE | Audittimestamp should be datetime and not date only. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
18 | POLINE | clicking TAB after QTY, and attempting to type does not work. Issue with UOM. TAB does not work after QTY field. |  |  | Bug | High | Hiba HALABI | Mohsan | Open
19 | POLINE | When a record cannot be inserted/edited in POLINE and procedure raises error, the error is not being reflected on application to the user, and the changes are discarded. | To reproduce, open a PO, and remove the QTY, UNITPRICE, and TOTALLINECOST from a given POLINE where LINETYPE = ITEM. Click save. The record is not saved, changes are discarded without returning to the user. |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
20 | Attachments | Error when trying to add a valid attachment |  | Figure 2 | Bug | High | Hiba HALABI | Mohsan | Fix Available
21 | POLINE | Do not auto update SUBCOST and TOTALCOST in POLINE header. |  |  | Bug | High | Hiba HALABI | Mohsan | Open
22 | Revise PO | Revise PO is not working. It should start by calling the procedure PO_GETNEXPOREV. If it returned an error, then the dialogbox should NOT show, and the same error should be returned to the user. Otherwise, display the dialog box showing in Revision, the returned revision number from procedure output. | To reproduce, go to Search PO, open PO 1006. Click Revise PO, the dialog box shows with wrong information. On the contrary, if you call the procedure, it returns an error! declare @nextrev smallint exec fsppo.dbo.PO_GetNextPORev '1006', '0', @OUTPUTNEXTREV = @nextrev OUTPUT print (@nextrev) |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available |  | I updated SP, Change in RaiseError, after that, I update in the code
23 | Change Status | Clicking on Change Status returns an error. | To reproduce, open registration #1006. Click on Change Status. It will return an error. |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
24 | Print PO | print PO should open in a NEW TAB. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
25 | View Revision History | Clicking on View Revision History returns an error. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
26 | PO | Opening any PO returns an error. See figure 3. |  | Figure 3 | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
27 | New Contract | Upon creating a new contract, clicking on Organization and attempting to select a given value does not work |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
28 | New Contract | Upon creating a new contract and filling into all values, clicking save returns no action! |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
29 | Load PO Template | Dialog box should show the below columns in order: - Template Name - Organization (Name) - project Name - Vendor Name - Created By No filter should be available on 'select' option. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
30 | Search PO Templates | Filters & grid output. Template Name Template Description Organization (filter) Project(filter) Vendor(filter) Created by (filter) Created after (calender) in the output, the link should be on Template ID (first column) which is the same behavior for Registration, Supplier, and PO. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
31 | Po Templates | Vendor ID/Vendor Name is not mandatory. Mandatory information are: Organization & Buyer |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
32 | PO Templates | Vendor ID/Vendor Name should be disabled and attain same behavior like PO. Unable to select a Vendor ID from dialog box. |  |  | Bug | Very High | Hiba HALABI | Mohsan | Fix Available
33 | PO Templates | Add audit information to the end of the PO Template Page. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available
34 | PO Templates | Add Template ID and Template Owner in the Templates Information section. Rename Templates Information to Template Header. Template Owner = Logged in user. The Template ID and Template owner will show upon saving, and when editing an existing template. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available
35 | PO/PoTemplates | Disable vendor ID from PO/Edit PO/PO Templates/Edit Po Template pages |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available
36 | Dialog boxes with filters | % should be accepted by all filters in dialog boxes. See Figure |  | Figure 4 | Enhancement | High | Hiba HALABI | Mohsan | Open
37 |  | Change datatype of ORDERTYPE, REQUIREDATE, VENDORDATE, and QUOTATIONDATE to DATE and not DATETIME in all relevant tables and procedures. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available
38 | PO | - When a purchase order is successfully created, return a confirmation message to be referred to from SS_MESSAGES. - When PO change Status is successfully applied, return confirmation message to user: Status successfully updated. |  |  | Enhancement | Medium | Hiba HALABI | Mohsan | Fix Available
39 | Errors | When an error is shown for any reason, if user removes the error, and apply any operation on the page, the old error is reshowing. |  |  | Bug | High | Hiba HALABI | Mohsan | Fix Available
40 | PO print | If only one supplier is defined, the grid should show only one line in Supplier Details. If VENDORATTN2NAME is null, show one row. Else, show 2 rows. |  |  | Enhancement | Low | Hiba HALABI | Mohsan | Open
41

## Figures
Figure 1
Figure 2
Figure 3
Figure 4

## POLINE
Action 1 | Action 2 | Status
NULL | Insert | not working for line 2 and beyond
Insert | Edit | Not working
NULL | Edit | working
NULL | Delete | working

## Sheet2 (hidden)
Type | Priority | Status
Bug | Low | Open
Regression | Medium | Fix Available
Enhancement | High | Failed
New Development | Very High | Passed
Missing Function |  | Cannot Reproduce
Cancelled